## owssvr
LOD:DC* | Is Checked out to local | Name | Item Child Count | LOD:DocNo-DocTitle | Rev | Doc-Status | W-Status | D-Version | Subm-Date | DT-Number | Shared With | IT-Number | CS-Received | Review Code | Remarks | CSR-ILF Reply-DueDate | LOD | LOD:Start-PLN | LOD:DIC-PLN | Item Type | Path
PM | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000_C1_IFR | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000-Project Master Document Register - Phase 3 | C1 | IFR | Completed/ Submitted | Historical | 2023-04-14 | TRN-00136 |  | E-mail | 2023-04-26 | C |  | 2023-05-03 | 345 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000_0_IFU | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000-Project Master Document Register - Phase 3 | 0 | IFU | Not Started | [9 empty] | 345 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000_C2_IFA | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000-Project Master Document Register - Phase 3 | C2 | IFA | IDCCheck completed | Current | 2023-05-15 | TRN-00230 |  | E-mail | 2023-05-23 | C |  | 2023-05-30 | 345 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000_C3_IFA | 0 | NAWCPF-ILFAE-NCPF-000-DC-REG-40000-Project Master Document Register - Phase 3 | C3 | IFA | Not Started | [9 empty] | 345 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405-Datasheet for Shutdown and Blowdown Valves | C1 | IFR | Not Started | [9 empty] | 149 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405-Datasheet for Shutdown and Blowdown Valves | 0 | IFU | Not Started | [9 empty] | 149 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40405-Datasheet for Shutdown and Blowdown Valves | C2 | IFA | Not Started | [9 empty] | 149 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406-Datasheet for Control Valves | C1 | IFR | Not Started | [9 empty] | 150 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406-Datasheet for Control Valves | 0 | IFU | Not Started | [9 empty] | 150 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40406-Datasheet for Control Valves | C2 | IFA | Not Started | [9 empty] | 150 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407-Datasheet for F&G Devices - IR Flame Detector | C1 | IFR | Not Started | [9 empty] | 151 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407-Datasheet for F&G Devices - IR Flame Detector | 0 | IFU | Not Started | [9 empty] | 151 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40407-Datasheet for F&G Devices - IR Flame Detector | C2 | IFA | Not Started | [9 empty] | 151 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408-Datasheet for Flowmeters | C1 | IFR | Not Started | [9 empty] | 152 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408-Datasheet for Flowmeters | 0 | IFU | Not Started | [9 empty] | 152 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40408-Datasheet for Flowmeters | C2 | IFA | Not Started | [9 empty] | 152 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409-Datasheet for Motor Operated Valves (MOV) | C1 | IFR | Not Started | [9 empty] | 153 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409-Datasheet for Motor Operated Valves (MOV) | 0 | IFU | Not Started | [9 empty] | 153 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40409-Datasheet for Motor Operated Valves (MOV) | C2 | IFA | Not Started | [9 empty] | 153 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410-Datasheet for Pressure Relief Valves | C1 | IFR | Not Started | [9 empty] | 154 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410-Datasheet for Pressure Relief Valves | 0 | IFU | Not Started | [9 empty] | 154 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40410-Datasheet for Pressure Relief Valves | C2 | IFA | Not Started | [9 empty] | 154 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411-Datasheets for Field Instruments - Pressure Transmitters | C1 | IFR | Not Started | [9 empty] | 155 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411-Datasheets for Field Instruments - Pressure Transmitters | 0 | IFU | Not Started | [9 empty] | 155 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40411-Datasheets for Field Instruments - Pressure Transmitters | C2 | IFA | Not Started | [9 empty] | 155 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430-Datasheet for F&G Devices - IR Point Gas Detector | C1 | IFR | Not Started | [9 empty] | 168 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430-Datasheet for F&G Devices - IR Point Gas Detector | 0 | IFU | Not Started | [9 empty] | 168 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40430-Datasheet for F&G Devices - IR Point Gas Detector | C2 | IFA | Not Started | [9 empty] | 168 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431-Datasheet for F&G Devices - Manual Alarm Call Point | C1 | IFR | Not Started | [9 empty] | 169 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431-Datasheet for F&G Devices - Manual Alarm Call Point | 0 | IFU | Not Started | [9 empty] | 169 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40431-Datasheet for F&G Devices - Manual Alarm Call Point | C2 | IFA | Not Started | [9 empty] | 169 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432-Datasheet for F&G Devices - Sounder Beacon | C1 | IFR | Not Started | [9 empty] | 170 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432-Datasheet for F&G Devices - Sounder Beacon | 0 | IFU | Not Started | [9 empty] | 170 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40432-Datasheet for F&G Devices - Sounder Beacon | C2 | IFA | Not Started | [9 empty] | 170 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433-Datasheets for Field Instruments - Restriction Orifice | C1 | IFR | Not Started | [9 empty] | 171 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433-Datasheets for Field Instruments - Restriction Orifice | 0 | IFU | Not Started | [9 empty] | 171 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40433-Datasheets for Field Instruments - Restriction Orifice | C2 | IFA | Not Started | [9 empty] | 171 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434-Datasheet for Junction Box | C1 | IFR | Not Started | [9 empty] | 172 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434-Datasheet for Junction Box | 0 | IFU | Not Started | [9 empty] | 172 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40434-Datasheet for Junction Box | C2 | IFA | Not Started | [9 empty] | 172 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435-Datasheet for Instrument Cable | C1 | IFR | Not Started | [9 empty] | 173 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435-Datasheet for Instrument Cable | 0 | IFU | Not Started | [9 empty] | 173 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40435-Datasheet for Instrument Cable | C2 | IFA | Not Started | [9 empty] | 173 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807-Datasheet for Telecom Equipment | C1 | IFR | Not Started | [9 empty] | 180 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807-Datasheet for Telecom Equipment | 0 | IFU | Not Started | [9 empty] | 180 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40807-Datasheet for Telecom Equipment | C2 | IFA | Not Started | [9 empty] | 180 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808-Datasheets for FO Cable | C1 | IFR | Completed/ Submitted | Current | 2023-05-19 | TRN-00250 |  |  | 2023-05-25 | C |  | 2023-06-01 | 181 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808-Datasheets for FO Cable | 0 | IFU | Not Started | [9 empty] | 181 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DAT-40808-Datasheets for FO Cable | C2 | IFA | Not Started | - | [5 empty] | C |  |  | 181 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401-Instrument Cable Block diagram | C1 | IFR | Not Started | [9 empty] | 146 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401-Instrument Cable Block diagram | 0 | IFU | Not Started | [9 empty] | 146 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40401-Instrument Cable Block diagram | C2 | IFA | Not Started | [9 empty] | 146 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418-F&G Cable Block Diagram | C1 | IFR | Not Started | [9 empty] | 158 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418-F&G Cable Block Diagram | 0 | IFU | Not Started | [9 empty] | 158 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40418-F&G Cable Block Diagram | C2 | IFA | Not Started | [9 empty] | 158 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419_C001_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419-UCP System Block Diagram | C001 | IFR | Completed/ Submitted | Historical | 2023-04-07 | TRN-00111 |  | E-mail | 2023-04-17 | B |  | 2023-04-24 | 73 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419-UCP System Block Diagram | 00 | IFU | Completed/ Submitted | Current | 2023-05-05 | [7 empty] | 73 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40419-UCP System Block Diagram | C2 | IFA | Completed/ Submitted | Historical | 2023-04-26 | TRN-00161 |  | E-mail | 2023-05-04 | D |  | 2023-05-11 | 73 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801-Telecom Network Block Diagram | C1 | IFR | Not Started | [9 empty] | 174 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801-Telecom Network Block Diagram | 0 | IFU | Not Started | [9 empty] | 174 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40801-Telecom Network Block Diagram | C2 | IFA | Not Started | [9 empty] | 174 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802-Process CCTV Block Diagram | C1 | IFR | Completed/ Submitted | Historical | 2023-05-05 | TRN-00189 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 175 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802-Process CCTV Block Diagram | 0 | IFU | Not Started | [9 empty] | 175 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802-Process CCTV Block Diagram | C2 | IFA | Completed/ Submitted | Current | 2023-05-19 | TRN-00246 |  | E-mail | 2023-05-25 | C |  | 2023-06-01 | 175 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40802-Process CCTV Block Diagram | C3 | IFA | Not Started | [9 empty] | 175 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803-PAGA System Block Diagram | C1 | IFR | Completed/ Submitted | Historical | 2023-05-12 | TRN-00217 |  | E-mail | 2023-05-18 | C |  | 2023-05-25 | 176 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803-PAGA System Block Diagram | 00 | IFU | Completed/ Submitted | Current | 2023-05-26 | TRN-00276 | [6 empty] | 176 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40803-PAGA System Block Diagram | C2 | IFA | Completed/ Submitted | Historical | 2023-05-22 | TRN-00256 |  | E-mail | 2023-05-25 | D |  | 2023-06-01 | 176 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804-FOC Block Diagram | C1 | IFR | Not Started | [9 empty] | 177 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804-FOC Block Diagram | 0 | IFU | Not Started | [9 empty] | 177 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DBD-40804-FOC Block Diagram | C2 | IFA | Not Started | [9 empty] | 177 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414_C001_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414-Interconnection Wiring Diagrams (Junction Box) | C001 | IFR | Not Started | [9 empty] | 80 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414_000_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414-Interconnection Wiring Diagrams (Junction Box) | 000 | IFU | Not Started | [9 empty] | 80 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414_C002_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DIA-40414-Interconnection Wiring Diagrams (Junction Box) | C002 | IFA | Not Started | [9 empty] | 80 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402-Instrument Cable Routing Drawing | C1 | IFR | Not Started | [9 empty] | 147 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402-Instrument Cable Routing Drawing | 0 | IFU | Not Started | [9 empty] | 147 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40402-Instrument Cable Routing Drawing | C2 | IFA | Not Started | [9 empty] | 147 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417-Control System Architecture Drawing | C1 | IFR | Completed/ Submitted | Historical | 2023-04-10 | TRN-00119 |  | E-mail | 2023-04-17 | D |  | 2023-04-24 | 74 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417-Control System Architecture Drawing | 00 | IFU | Completed/ Submitted | Current | 2023-04-18 | TRN-00146 | [6 empty] | 74 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40417-Control System Architecture Drawing | C2 | IFA | Not Started | [9 empty] | 74 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425-Fire and Gas Detection System Overview Schematic | C1 | IFR | Not Started | [9 empty] | 163 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425-Fire and Gas Detection System Overview Schematic | 0 | IFU | Not Started | [9 empty] | 163 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40425-Fire and Gas Detection System Overview Schematic | C2 | IFA | Not Started | [9 empty] | 163 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426-Loop Drawings | C1 | IFR | Not Started | [9 empty] | 164 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426-Loop Drawings | 0 | IFU | Not Started | [9 empty] | 164 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40426-Loop Drawings | C2 | IFA | Not Started | [9 empty] | 164 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428-Hook Up Drawings | C1 | IFR | Not Started | [9 empty] | 166 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428-Hook Up Drawings | 0 | IFU | Not Started | [9 empty] | 166 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40428-Hook Up Drawings | C2 | IFA | Not Started | [9 empty] | 166 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429-Installation Drawings | C1 | IFR | Completed/ Submitted | Current | 2023-05-16 | TRN-00239 |  | E-mail | 2023-05-25 | C |  | 2023-06-01 | 167 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429-Installation Drawings | 0 | IFU | Not Started | [9 empty] | 167 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-DRW-40429-Installation Drawings | C2 | IFA | Not Started | [9 empty] | 167 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415-Instrument and JB location layout | C1 | IFR | Not Started | [9 empty] | 157 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415-Instrument and JB location layout | 0 | IFU | Not Started | [9 empty] | 157 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40415-Instrument and JB location layout | C2 | IFA | Not Started | [9 empty] | 157 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809-Telecom Equipment Location and Cable Routing layout | C1 | IFR | Not Started | [9 empty] | 182 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809-Telecom Equipment Location and Cable Routing layout | 0 | IFU | Not Started | [9 empty] | 182 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LAY-40809-Telecom Equipment Location and Cable Routing layout | C2 | IFA | Not Started | [9 empty] | 182 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403-Instrument List | C1 | IFR | Not Started | [9 empty] | 148 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403-Instrument List | 0 | IFU | Not Started | [9 empty] | 148 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40403-Instrument List | C2 | IFA | Not Started | [9 empty] | 148 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420-F&G I/O List | C1 | IFR | Not Started | [9 empty] | 159 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420-F&G I/O List | 0 | IFU | Not Started | [9 empty] | 159 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40420-F&G I/O List | C2 | IFA | Not Started | [9 empty] | 159 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421-Control & Instrumentation Cable List | C1 | IFR | Not Started | [9 empty] | 160 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421-Control & Instrumentation Cable List | 0 | IFU | Not Started | [9 empty] | 160 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40421-Control & Instrumentation Cable List | C2 | IFA | Not Started | [9 empty] | 160 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423-F&G System Cable List | C1 | IFR | Not Started | [9 empty] | 162 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423-F&G System Cable List | 0 | IFU | Not Started | [9 empty] | 162 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40423-F&G System Cable List | C2 | IFA | Not Started | [9 empty] | 162 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806-Telecom Equipment List | C1 | IFR | Not Started | [9 empty] | 179 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806-Telecom Equipment List | 0 | IFU | Not Started | [9 empty] | 179 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-LST-40806-Telecom Equipment List | C2 | IFA | Not Started | [9 empty] | 179 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427-Instrumentation (MTO) | C1 | IFR | Not Started | [9 empty] | 165 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427-Instrumentation (MTO) | 0 | IFU | Not Started | [9 empty] | 165 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40427-Instrumentation (MTO) | C2 | IFA | Not Started | [9 empty] | 165 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811-Telecom Bulk Material Take off (MTO) | C1 | IFR | Not Started | [9 empty] | 184 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811-Telecom Bulk Material Take off (MTO) | 0 | IFU | Not Started | [9 empty] | 184 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-MTO-40811-Telecom Bulk Material Take off (MTO) | C2 | IFA | Not Started | [9 empty] | 184 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412-Junction Box Schedule | C1 | IFR | Not Started | [9 empty] | 156 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412-Junction Box Schedule | 0 | IFU | Not Started | [9 empty] | 156 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40412-Junction Box Schedule | C2 | IFA | Not Started | [9 empty] | 156 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413_C001_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413-Control & Instrumentation Cable List | C001 | IFR | Not Started | [9 empty] | 79 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413_000_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413-Control & Instrumentation Cable List | 000 | IFU | Not Started | [9 empty] | 79 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413_C002_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40413-Control & Instrumentation Cable List | C002 | IFA | Not Started | [9 empty] | 79 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810-Telecom Cable Schedule | C1 | IFR | Not Started | [9 empty] | 183 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810-Telecom Cable Schedule | 0 | IFU | Not Started | [9 empty] | 183 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SCH-40810-Telecom Cable Schedule | C2 | IFA | Not Started | [9 empty] | 183 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416-SOW for ICSS Modification | C1 | IFR | Not Started | [9 empty] | 75 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416_000_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416-SOW for ICSS Modification | 000 | IFU | Not Started | [9 empty] | 75 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40416-SOW for ICSS Modification | C2 | IFA | Not Started | [9 empty] | 75 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812-SOW for Telecom System Modifications | C1 | IFR | Not Started | [9 empty] | 185 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812-SOW for Telecom System Modifications | 0 | IFU | Not Started | [9 empty] | 185 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SOW-40812-SOW for Telecom System Modifications | C2 | IFA | Not Started | [9 empty] | 185 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424-Control & Instrumentation Specification for Packaged Equipment | C1 | IFR | Completed/ Submitted | Historical | 2023-03-28 | TRN-00082 |  | E-mail | 2023-04-04 | B |  | 2023-04-11 | 84 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424-Control & Instrumentation Specification for Packaged Equipment | 00 | IFU | Completed/ Submitted | Current | 2023-04-27 | TRN-00162 | [6 empty] | 84 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40424-Control & Instrumentation Specification for Packaged Equipment | C2 | IFA | Completed/ Submitted | Historical | 2023-04-13 | TRN-00125 |  | E-mail | 2023-04-26 | D |  | 2023-05-03 | 84 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805-Telecommunication System Specification | C1 | IFR | Completed/ Submitted | Historical | 2023-04-04 | TRN-00096 |  | E-mail | 2023-04-11 | C |  | 2023-04-18 | 178 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805-Telecommunication System Specification | 0 | IFU | Completed/ Submitted | Current | 2023-05-16 | TRN-00238 | [6 empty] | 178 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805-Telecommunication System Specification | C2 | IFA | Completed/ Submitted | Historical | 2023-04-18 | TRN-00144 |  | E-mail | 2023-04-27 | C |  | 2023-05-04 | 178 |  |  | Folder | sites/15195/14_DELV
TL | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-CI-SPE-40805-Telecommunication System Specification | C3 | IFA | Completed/ Submitted | Historical | 2023-05-05 | TRN-00188 |  | E-mail | 2023-05-15 | D |  | 2023-05-22 | 178 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214_C001_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214-Design Calculation Minor Foundations | C001 | IFR | Not Started | [9 empty] | 24 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214-Design Calculation Minor Foundations | 00 | IFU | Not Started | [9 empty] | 24 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40214-Design Calculation Minor Foundations | C2 | IFA | Not Started | [9 empty] | 24 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238-Design Calculation for Details Pipe Rack Foundation | C1 | IFR | Not Started | [9 empty] | 301 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238-Design Calculation for Details Pipe Rack Foundation | 0 | IFU | Not Started | [9 empty] | 301 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40238-Design Calculation for Details Pipe Rack Foundation | C2 | IFA | Not Started | [9 empty] | 301 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239-Design Calculation for Special Piping Supports Foundation | C1 | IFR | Not Started | [9 empty] | 302 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239-Design Calculation for Special Piping Supports Foundation | 0 | IFU | Not Started | [9 empty] | 302 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40239-Design Calculation for Special Piping Supports Foundation | C2 | IFA | Not Started | [9 empty] | 302 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240-Design Calculation for Bridge Pipe Rack Foundation | C1 | IFR | Not Started | [9 empty] | 303 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240-Design Calculation for Bridge Pipe Rack Foundation | 0 | IFU | Not Started | [9 empty] | 303 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40240-Design Calculation for Bridge Pipe Rack Foundation | C2 | IFA | Not Started | [9 empty] | 303 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245-Design Calculation for E&I Container Foundation | C1 | IFR | Not Started | [9 empty] | 308 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245-Design Calculation for E&I Container Foundation | 0 | IFU | Not Started | [9 empty] | 308 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40245-Design Calculation for E&I Container Foundation | C2 | IFA | Not Started | [9 empty] | 308 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246-Design Calculation for Gas Engine Water Cooler Foundation | C1 | IFR | Not Started | [9 empty] | 309 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246-Design Calculation for Gas Engine Water Cooler Foundation | 0 | IFU | Not Started | [9 empty] | 309 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40246-Design Calculation for Gas Engine Water Cooler Foundation | C2 | IFA | Not Started | [9 empty] | 309 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254-Design Calculation for Pipe Rack | C1 | IFR | Not Started | [9 empty] | 317 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254-Design Calculation for Pipe Rack | 0 | IFU | Not Started | [9 empty] | 317 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40254-Design Calculation for Pipe Rack | C2 | IFA | Not Started | [9 empty] | 317 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255-Design Calculation for Special Piping Supports | C1 | IFR | Not Started | [9 empty] | 318 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255-Design Calculation for Special Piping Supports | 0 | IFU | Not Started | [9 empty] | 318 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40255-Design Calculation for Special Piping Supports | C2 | IFA | Not Started | [9 empty] | 318 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256-Design Calculation for Bridge Pipe Rack | C1 | IFR | Not Started | [9 empty] | 319 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256-Design Calculation for Bridge Pipe Rack | 0 | IFU | Not Started | [9 empty] | 319 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-CAL-40256-Design Calculation for Bridge Pipe Rack | C2 | IFA | Not Started | [9 empty] | 319 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207-Standard drawings - General Notes and Legends | C1 | IFR | Completed/ Submitted | Historical | 2023-05-09 | TRN-00207 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 17 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207-Standard drawings - General Notes and Legends | 00 | IFU | Completed/ Submitted | Current | 2023-05-26 | TRN-00272 | [6 empty] | 17 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40207-Standard drawings - General Notes and Legends | C2 | IFA | Completed/ Submitted | Historical | 2023-05-19 | TRN-00248 |  | E-mail | 2023-05-25 | D |  | 2023-06-01 | 17 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208-Typical drawings for Anchor bolt | C1 | IFR | Completed/ Submitted | Historical | 2023-05-18 | TRN-00242 |  | E-mail | 2023-05-23 | C |  | 2023-05-30 | 18 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208-Typical drawings for Anchor bolt | 00 | IFU | Not Started | [9 empty] | 18 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40208-Typical drawings for Anchor bolt | C2 | IFA | Completed/ Submitted | Current | 2023-05-24 | TRN-00264 | [6 empty] | 18 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209-Typical cable trench and duct bank details | C1 | IFR | DIC Approved | Historical | 2023-05-19 | TRN-00252 |  | E-mail | 2023-05-25 | D |  | 2023-06-01 | 19 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209-Typical cable trench and duct bank details | 00 | IFU | Completed/ Submitted | Current | 2023-05-26 | TRN-00273 | [6 empty] | 19 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40209-Typical cable trench and duct bank details | C2 | IFA | Not Started | [9 empty] | 19 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210-Typical road and paving detail drawings | C1 | IFR | Completed/ Submitted | Current | 2023-05-25 | TRN-00269 | [6 empty] | 20 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210-Typical road and paving detail drawings | 00 | IFU | Not Started | [9 empty] | 20 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40210-Typical road and paving detail drawings | C2 | IFA | Not Started | [9 empty] | 20 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211-Typical fence and gate detail drawings | C1 | IFR | Completed/ Submitted | Current | 2023-05-25 | TRN-00267 | [6 empty] | 21 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211-Typical fence and gate detail drawings | 00 | IFU | Not Started | [9 empty] | 21 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40211-Typical fence and gate detail drawings | C2 | IFA | Not Started | [9 empty] | 21 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212-Typical details for concrete protection slabs | C1 | IFR | Not Started | [9 empty] | 22 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212-Typical details for concrete protection slabs | 00 | IFU | Not Started | [9 empty] | 22 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40212-Typical details for concrete protection slabs | C2 | IFA | Not Started | [9 empty] | 22 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213-Typical details for lighting pole foundation | C1 | IFR | Completed/ Submitted | Historical | 2023-05-19 | TRN-00253 |  | E-mail | 2023-05-25 | D |  | 2023-06-01 | 23 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213-Typical details for lighting pole foundation | 00 | IFU | Completed/ Submitted | Current | 2023-05-26 | TRN-00274 | [6 empty] | 23 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40213-Typical details for lighting pole foundation | C2 | IFA | Not Started | [9 empty] | 23 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215-Typical details for Lifting System foundation | C1 | IFR | Not Started | [9 empty] | 25 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215-Typical details for Lifting System foundation | 00 | IFU | Not Started | [9 empty] | 25 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40215-Typical details for Lifting System foundation | C2 | IFA | Not Started | [9 empty] | 25 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217-Typical foundation details for wind stock | C1 | IFR | Not Started | [9 empty] | 27 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217-Typical foundation details for wind stock | 00 | IFU | Not Started | [9 empty] | 27 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40217-Typical foundation details for wind stock | C2 | IFA | Not Started | [9 empty] | 27 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218-Typical foundation details for bollards and crash barriers | C1 | IFR | Not Started | [9 empty] | 28 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218-Typical foundation details for bollards and crash barriers | 00 | IFU | Not Started | [9 empty] | 28 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40218-Typical foundation details for bollards and crash barriers | C2 | IFA | Not Started | [9 empty] | 28 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226-Foundation Plan & Details of Special Piping Supports | C1 | IFR | Not Started | [9 empty] | 295 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226-Foundation Plan & Details of Special Piping Supports | 0 | IFU | Not Started | [9 empty] | 295 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40226-Foundation Plan & Details of Special Piping Supports | C2 | IFA | Not Started | [9 empty] | 295 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227-Foundation Plan & Details of Bridge Pipe Rack | C1 | IFR | Not Started | [9 empty] | 369 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227-Foundation Plan & Details of Bridge Pipe Rack | 0 | IFU | Not Started | [9 empty] | 369 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40227-Foundation Plan & Details of Bridge Pipe Rack | C2 | IFA | Not Started | [9 empty] | 369 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232-Foundation Plan & Details of E&I Container | C1 | IFR | Not Started | [9 empty] | 373 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232-Foundation Plan & Details of E&I Container | 0 | IFU | Not Started | [9 empty] | 373 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40232-Foundation Plan & Details of E&I Container | C2 | IFA | Not Started | [9 empty] | 373 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233-Foundation Plan & Details of Gas Engine Water Cooler | C1 | IFR | Not Started | [9 empty] | 368 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233-Foundation Plan & Details of Gas Engine Water Cooler | 0 | IFU | Not Started | [9 empty] | 368 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40233-Foundation Plan & Details of Gas Engine Water Cooler | C2 | IFA | Not Started | [9 empty] | 368 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234-Plan & Details of Instrumentation Pit | C1 | IFR | Not Started | [9 empty] | 297 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234-Plan & Details of Instrumentation Pit | 0 | IFU | Not Started | [9 empty] | 297 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40234-Plan & Details of Instrumentation Pit | C2 | IFA | Not Started | [9 empty] | 297 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248-Structural Steel Plan & Details of Pipe Rack | C1 | IFR | Not Started | [9 empty] | 311 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248-Structural Steel Plan & Details of Pipe Rack | 0 | IFU | Not Started | [9 empty] | 311 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40248-Structural Steel Plan & Details of Pipe Rack | C2 | IFA | Not Started | [9 empty] | 311 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249-Structural Steel Plan & Details of Special Piping Supports | C1 | IFR | Not Started | [9 empty] | 312 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249-Structural Steel Plan & Details of Special Piping Supports | 0 | IFU | Not Started | [9 empty] | 312 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40249-Structural Steel Plan & Details of Special Piping Supports | C2 | IFA | Not Started | [9 empty] | 312 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250-Structural Steel Plan & Details of Bridge Pipe Rack | C1 | IFR | Not Started | [9 empty] | 313 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250-Structural Steel Plan & Details of Bridge Pipe Rack | 0 | IFU | Not Started | [9 empty] | 313 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40250-Structural Steel Plan & Details of Bridge Pipe Rack | C2 | IFA | Not Started | [9 empty] | 313 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251-Structural Steel Plan & Details of Access Platforms | C1 | IFR | Not Started | [9 empty] | 314 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251-Structural Steel Plan & Details of Access Platforms | 0 | IFU | Not Started | [9 empty] | 314 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40251-Structural Steel Plan & Details of Access Platforms | C2 | IFA | Not Started | [9 empty] | 314 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252-Foundation details for Access Platform | C1 | IFR | Not Started | [9 empty] | 315 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252-Foundation details for Access Platform | 0 | IFU | Not Started | [9 empty] | 315 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40252-Foundation details for Access Platform | C2 | IFA | Not Started | [9 empty] | 315 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257-Miscellaneous detail drawings | C1 | IFR | Not Started | [9 empty] | 320 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257-Miscellaneous detail drawings | 0 | IFU | Not Started | [9 empty] | 320 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40257-Miscellaneous detail drawings | C2 | IFA | Not Started | [9 empty] | 320 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258-PCC/RCC Works | C1 | IFR | Not Started | [9 empty] | 321 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258-PCC/RCC Works | 0 | IFU | Not Started | [9 empty] | 321 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40258-PCC/RCC Works | C2 | IFA | Not Started | [9 empty] | 321 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259-Structural Steel Works | C1 | IFR | Not Started | [9 empty] | 322 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259-Structural Steel Works | 0 | IFU | Not Started | [9 empty] | 322 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40259-Structural Steel Works | C2 | IFA | Not Started | [9 empty] | 322 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260-Modification drawings for existing substation - Architectural | C1 | IFR | Not Started | [9 empty] | 323 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260-Modification drawings for existing substation - Architectural | 0 | IFU | Not Started | [9 empty] | 323 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40260-Modification drawings for existing substation - Architectural | C2 | IFA | Not Started | [9 empty] | 323 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261-Modification drawings for existing substation - Structural | C1 | IFR | Not Started | [9 empty] | 324 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261-Modification drawings for existing substation - Structural | 0 | IFU | Not Started | [9 empty] | 324 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-DRW-40261-Modification drawings for existing substation - Structural | C2 | IFA | Not Started | [9 empty] | 324 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219-Site grading layout drawing | C1 | IFR | DIC Approved | [9 empty] | 29 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219-Site grading layout drawing | 00 | IFU | Not Started | [9 empty] | 29 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40219-Site grading layout drawing | C2 | IFA | Not Started | [9 empty] | 29 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220-Road, pavement, fence and gate layout drawing | C1 | IFR | Not Started | [9 empty] | 30 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220-Road, pavement, fence and gate layout drawing | 00 | IFU | Not Started | [9 empty] | 30 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40220-Road, pavement, fence and gate layout drawing | C2 | IFA | Not Started | [9 empty] | 30 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221-Civil UG layout | C1 | IFR | Not Started | [9 empty] | 31 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221-Civil UG layout | 00 | IFU | Not Started | [9 empty] | 31 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40221-Civil UG layout | C2 | IFA | Not Started | [9 empty] | 31 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265-Civil Layout | C1 | IFR | Not Started | [9 empty] | 328 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265-Civil Layout | 0 | IFU | Not Started | [9 empty] | 328 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-LAY-40265-Civil Layout | C2 | IFA | Not Started | [9 empty] | 328 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262-Adequacy check report for existing substation (if required) | C1 | IFR | Not Started | [9 empty] | 325 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262-Adequacy check report for existing substation (if required) | 0 | IFU | Not Started | [9 empty] | 325 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-CV-REP-40262-Adequacy check report for existing substation (if required) | C2 | IFA | Not Started | [9 empty] | 325 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-NCPF-000-PM-PRO-40105_C1_IFR | 2 | NAWCPF-ILFAE-PF01-000-DC-PRO-40105-Document Control Procedures | C1 | IFR | IDCCheck completed | Historical | 2023-03-03 | TRN-00025 |  | E-mail | 2023-03-16 | C |  | 2023-03-23 | 4 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-DC-PRO-40105_00_IFU | 3 | NAWCPF-ILFAE-PF01-000-DC-PRO-40105-Document Control Procedures | 00 | IFU | Completed/ Submitted | Current | 2023-04-06 | TRN-00106 | [6 empty] | 4 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-DC-PRO-40105_C2_IFA | 6 | NAWCPF-ILFAE-PF01-000-DC-PRO-40105-Document Control Procedures | C2 | IFA | Completed/ Submitted | Historical | 2023-03-22 | TRN-00066 |  | E-mail | 2023-04-05 | D |  | 2023-04-12 | 4 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301-Cable Sizing Calculation | C1 | IFR | Not Started | [9 empty] | 85 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301-Cable Sizing Calculation | 0 | IFU | Not Started | [9 empty] | 85 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40301-Cable Sizing Calculation | C2 | IFA | Not Started | [9 empty] | 85 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327-Earthing Calculation | C1 | IFR | Not Started | [9 empty] | 214 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327-Earthing Calculation | 0 | IFU | Not Started | [9 empty] | 214 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40327-Earthing Calculation | C2 | IFA | Not Started | [9 empty] | 214 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328-Lightning Calculation | C1 | IFR | Not Started | [9 empty] | 215 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328-Lightning Calculation | 0 | IFU | Not Started | [9 empty] | 215 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-CAL-40328-Lightning Calculation | C2 | IFA | Not Started | [9 empty] | 215 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302_C1_IFR | 2 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302-VSD Datasheets | C1 | IFR | Completed/ Submitted | Historical | 2023-05-09 | TRN-00206 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 186 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302-VSD Datasheets | 0 | IFU | Not Started | [9 empty] | 186 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40302-VSD Datasheets | C2 | IFA | Completed/ Submitted | Current | 2023-05-24 | TRN-00263 | [6 empty] | 186 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334-MV Switchgears Datasheets | C1 | IFR | Completed/ Submitted | Historical | 2023-05-05 | TRN-00197 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 187 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334-MV Switchgears Datasheets | 00 | IFU | Completed/ Submitted | Current | 2023-05-25 | TRN-00266 | [6 empty] | 187 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40334-MV Switchgears Datasheets | C2 | IFA | Completed/ Submitted | Historical | 2023-05-18 | TRN-00240 |  | E-mail | 2023-05-24 | D |  | 2023-05-31 | 187 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335-Hamonic Filter Datasheet | C1 | IFR | Not Started | [9 empty] | 188 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335-Hamonic Filter Datasheet | 0 | IFU | Not Started | [9 empty] | 188 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40335-Hamonic Filter Datasheet | C2 | IFA | Not Started | [9 empty] | 188 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336-Electrical Cable Datasheet | C1 | IFR | Completed/ Submitted | Historical | 2023-05-05 | TRN-00198 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 189 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336-Electrical Cable Datasheet | 0 | IFU | Not Started | [9 empty] | 189 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DAT-40336-Electrical Cable Datasheet | C2 | IFA | Completed/ Submitted | Current | 2023-05-23 | TRN-00262 | [6 empty] | 189 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308-Underground Cable Routing | C1 | IFR | Not Started | [9 empty] | 195 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308-Underground Cable Routing | 0 | IFU | Not Started | [9 empty] | 195 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40308-Underground Cable Routing | C2 | IFA | Not Started | [9 empty] | 195 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326-Installation Drawing (Lighting, Earthing, Cabling) | C1 | IFR | Not Started | [9 empty] | 213 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326-Installation Drawing (Lighting, Earthing, Cabling) | 0 | IFU | Not Started | [9 empty] | 213 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40326-Installation Drawing (Lighting, Earthing, Cabling) | C2 | IFA | Not Started | [9 empty] | 213 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330-Interconnection Drawings | C1 | IFR | Not Started | [9 empty] | 217 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330-Interconnection Drawings | 0 | IFU | Not Started | [9 empty] | 217 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DRW-40330-Interconnection Drawings | C2 | IFA | Not Started | [9 empty] | 217 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303-CPF Emergency LV Switchgear - SLD | C1 | IFR | Not Started | [9 empty] | 190 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303-CPF Emergency LV Switchgear - SLD | 0 | IFU | Not Started | [9 empty] | 190 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40303-CPF Emergency LV Switchgear - SLD | C2 | IFA | Not Started | [9 empty] | 190 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304-CPF Main LV Switchgear - SLD | C1 | IFR | Not Started | [9 empty] | 191 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304-CPF Main LV Switchgear - SLD | 0 | IFU | Not Started | [9 empty] | 191 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40304-CPF Main LV Switchgear - SLD | C2 | IFA | Not Started | [9 empty] | 191 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305-CPF UPS for Switchgear Auxiliaries - SLD | C1 | IFR | Not Started | [9 empty] | 192 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305-CPF UPS for Switchgear Auxiliaries - SLD | 0 | IFU | Not Started | [9 empty] | 192 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40305-CPF UPS for Switchgear Auxiliaries - SLD | C2 | IFA | Not Started | [9 empty] | 192 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306-CPF UPS for DCS, Metering, Analysers - SLD | C1 | IFR | Not Started | [9 empty] | 193 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306-CPF UPS for DCS, Metering, Analysers - SLD | 0 | IFU | Not Started | [9 empty] | 193 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40306-CPF UPS for DCS, Metering, Analysers - SLD | C2 | IFA | Not Started | [9 empty] | 193 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307-CPF UPS for ESD, F&G - SLD - Power Distribution | C1 | IFR | Not Started | [9 empty] | 194 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307-CPF UPS for ESD, F&G - SLD - Power Distribution | 0 | IFU | Not Started | [9 empty] | 194 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40307-CPF UPS for ESD, F&G - SLD - Power Distribution | C2 | IFA | Not Started | [9 empty] | 194 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309-Key Single Line Diagram | C1 | IFR | Not Started | [9 empty] | 196 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309-Key Single Line Diagram | 0 | IFU | Not Started | [9 empty] | 196 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40309-Key Single Line Diagram | C2 | IFA | Not Started | [9 empty] | 196 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331-CPF Main MV Switchgear - SLD | C1 | IFR | Not Started | [9 empty] | 218 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331-CPF Main MV Switchgear - SLD | 0 | IFU | Not Started | [9 empty] | 218 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-DSL-40331-CPF Main MV Switchgear - SLD | C2 | IFA | Not Started | [9 empty] | 218 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310-Earthing & Lightning Protection Layout | C1 | IFR | Not Started | [9 empty] | 197 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310-Earthing & Lightning Protection Layout | 0 | IFU | Not Started | [9 empty] | 197 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40310-Earthing & Lightning Protection Layout | C2 | IFA | Not Started | [9 empty] | 197 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311-Outdoor Lighting and Small Power Layout | C1 | IFR | Not Started | [9 empty] | 198 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311-Outdoor Lighting and Small Power Layout | 0 | IFU | Not Started | [9 empty] | 198 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40311-Outdoor Lighting and Small Power Layout | C2 | IFA | Not Started | [9 empty] | 198 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312-CPF Substation Container ELE Equipment Layout | C1 | IFR | Not Started | [9 empty] | 199 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312-CPF Substation Container ELE Equipment Layout | 0 | IFU | Not Started | [9 empty] | 199 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40312-CPF Substation Container ELE Equipment Layout | C2 | IFA | Not Started | [9 empty] | 199 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324-CPF Substation GA Equipment Layout | C1 | IFR | Not Started | [9 empty] | 211 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324-CPF Substation GA Equipment Layout | 0 | IFU | Not Started | [9 empty] | 211 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40324-CPF Substation GA Equipment Layout | C2 | IFA | Not Started | [9 empty] | 211 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329-Cable routing Layout | C1 | IFR | Not Started | [9 empty] | 216 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329-Cable routing Layout | 0 | IFU | Not Started | [9 empty] | 216 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LAY-40329-Cable routing Layout | C2 | IFA | Not Started | [9 empty] | 216 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313-Electrical Power & Control Cables List | C1 | IFR | Not Started | [9 empty] | 200 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313-Electrical Power & Control Cables List | 0 | IFU | Not Started | [9 empty] | 200 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40313-Electrical Power & Control Cables List | C2 | IFA | Not Started | [9 empty] | 200 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314-Electrical Consumer Load List | C1 | IFR | Not Started | [9 empty] | 201 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314-Electrical Consumer Load List | 0 | IFU | Not Started | [9 empty] | 201 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40314-Electrical Consumer Load List | C2 | IFA | Not Started | [9 empty] | 201 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316-DC UPS Electrical Consumer List - CPF | C1 | IFR | Not Started | [9 empty] | 203 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316-DC UPS Electrical Consumer List - CPF | 0 | IFU | Not Started | [9 empty] | 203 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40316-DC UPS Electrical Consumer List - CPF | C2 | IFA | Not Started | [9 empty] | 203 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317-Electrical Equipment List | C1 | IFR | Not Started | [9 empty] | 204 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317-Electrical Equipment List | 0 | IFU | Not Started | [9 empty] | 204 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40317-Electrical Equipment List | C2 | IFA | Not Started | [9 empty] | 204 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318-AC UPS Electrical Consumer List - CPF | C1 | IFR | Not Started | [9 empty] | 205 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318-AC UPS Electrical Consumer List - CPF | 0 | IFU | Not Started | [9 empty] | 205 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-LST-40318-AC UPS Electrical Consumer List - CPF | C2 | IFA | Not Started | [9 empty] | 205 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319-Electrical MTO | C1 | IFR | Not Started | [9 empty] | 206 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319-Electrical MTO | 0 | IFU | Not Started | [9 empty] | 206 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-MTO-40319-Electrical MTO | C2 | IFA | Not Started | [9 empty] | 206 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320-Layout Main Cable Tray Plan | C1 | IFR | Not Started | [9 empty] | 207 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320-Layout Main Cable Tray Plan | 0 | IFU | Not Started | [9 empty] | 207 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-PLA-40320-Layout Main Cable Tray Plan | C2 | IFA | Not Started | [9 empty] | 207 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321-Power System Studies Report (ETAP Model) (Load Flow, Short Circuit & Motor Starting) | C1 | IFR | Not Started | [9 empty] | 208 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321-Power System Studies Report (ETAP Model) (Load Flow, Short Circuit & Motor Starting) | 0 | IFU | Not Started | [9 empty] | 208 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40321-Power System Studies Report (ETAP Model) (Load Flow, Short Circuit & Motor Starting) | C2 | IFA | Not Started | [9 empty] | 208 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332-Adequacy Report | C1 | IFR | Not Started | [9 empty] | 219 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332-Adequacy Report | 0 | IFU | Not Started | [9 empty] | 219 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-REP-40332-Adequacy Report | C2 | IFA | Not Started | [9 empty] | 219 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315-LV Distribution Boards Load/Panel Schedule - CPF | C1 | IFR | Not Started | [9 empty] | 202 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315-LV Distribution Boards Load/Panel Schedule - CPF | 0 | IFU | Not Started | [9 empty] | 202 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40315-LV Distribution Boards Load/Panel Schedule - CPF | C2 | IFA | Not Started | [9 empty] | 202 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325-Electrical Cable and Drum Schedule | C1 | IFR | Not Started | [9 empty] | 212 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325-Electrical Cable and Drum Schedule | 0 | IFU | Not Started | [9 empty] | 212 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SCH-40325-Electrical Cable and Drum Schedule | C2 | IFA | Not Started | [9 empty] | 212 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322-Technical Specification for Electrical Works | C1 | IFR | Completed/ Submitted | Historical | 2023-04-11 | TRN-00123 |  | E-mail | 2023-04-18 | C |  | 2023-04-25 | 209 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322-Technical Specification for Electrical Works | 0 | IFU | Not Started | [9 empty] | 209 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322-Technical Specification for Electrical Works | C2 | IFA | Completed/ Submitted | Historical | 2023-04-28 | TRN-00171 |  | E-mail | 2023-05-05 | C |  | 2023-05-12 | 209 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322-Technical Specification for Electrical Works | C3 | IFA | Completed/ Submitted | Current | 2023-05-19 | TRN-00251 |  | E-mail | 2023-05-26 | C |  | 2023-06-02 | 209 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322_C4_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40322-Technical Specification for Electrical Works | C4 | IFA | Not Started | [9 empty] | 209 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323-Electrical Specification for Packaged Equipment | C1 | IFR | Completed/ Submitted | Historical | 2023-04-07 | TRN-00112 |  | E-mail | 2023-04-17 | C |  | 2023-04-24 | 210 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323-Electrical Specification for Packaged Equipment | 00 | IFU | Completed/ Submitted | Current | 2023-05-19 | TRN-00249 | [6 empty] | 210 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323-Electrical Specification for Packaged Equipment | C2 | IFA | Completed/ Submitted | Historical | 2023-04-26 | TRN-00160 |  | E-mail | 2023-05-04 | C |  | 2023-05-11 | 210 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40323-Electrical Specification for Packaged Equipment | C3 | IFA | Completed/ Submitted | Historical | 2023-05-12 | TRN-00226 |  | E-mail | 2023-05-18 | D |  | 2023-05-25 | 210 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333-Specification for Electrical Equipment (As Required) | C1 | IFR | Not Started | [9 empty] | 220 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333-Specification for Electrical Equipment (As Required) | 0 | IFU | Not Started | [9 empty] | 220 |  |  | Folder | sites/15195/14_DELV
EL | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-EL-SPE-40333-Specification for Electrical Equipment (As Required) | C2 | IFA | Not Started | [9 empty] | 220 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913-Fire Water Demand Calculations | C1 | IFR | Completed/ Submitted | Historical | 2023-05-12 | TRN-00219 |  | E-mail | 2023-05-18 | C |  | 2023-05-25 | 338 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913-Fire Water Demand Calculations | 00 | IFU | Not Started | [9 empty] | 338 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-CAL-40913-Fire Water Demand Calculations | C2 | IFA | Completed/ Submitted | Current | 2023-05-25 | TRN-00268 |  | E-mail | 2023-05-26 | D |  | 2023-06-02 | 338 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912-Fire Fighting and Safety Equipment Datasheets | C1 | IFR | Not Started | [9 empty] | 337 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912-Fire Fighting and Safety Equipment Datasheets | 0 | IFU | Not Started | [9 empty] | 337 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-DAT-40912-Fire Fighting and Safety Equipment Datasheets | C2 | IFA | Not Started | [9 empty] | 337 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907-Fire & Gas Cause & Effect Chart | C1 | IFR | Not Started | [9 empty] | 332 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907-Fire & Gas Cause & Effect Chart | 0 | IFU | Not Started | [9 empty] | 332 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-DCE-40907-Fire & Gas Cause & Effect Chart | C2 | IFA | Not Started | [9 empty] | 332 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903-Fire & Gas Detection System Description | C1 | IFR | Not Started | [9 empty] | 329 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903-Fire & Gas Detection System Description | 0 | IFU | Not Started | [9 empty] | 329 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-JDS-40903-Fire & Gas Detection System Description | C2 | IFA | Not Started | [9 empty] | 329 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906-Fire & Gas Layout Drawings | C1 | IFR | Not Started | [9 empty] | 331 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906-Fire & Gas Layout Drawings | 0 | IFU | Not Started | [9 empty] | 331 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40906-Fire & Gas Layout Drawings | C2 | IFA | Not Started | [9 empty] | 331 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910-Hazardous Area Classification Layout | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00275 | [6 empty] | 335 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910-Hazardous Area Classification Layout | 0 | IFU | Not Started | [9 empty] | 335 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40910-Hazardous Area Classification Layout | C2 | IFA | Not Started | [9 empty] | 335 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911-Fire Fighting and Safety Equipment Layout | C1 | IFR | Not Started | [9 empty] | 336 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911-Fire Fighting and Safety Equipment Layout | 0 | IFU | Not Started | [9 empty] | 336 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-LAY-40911-Fire Fighting and Safety Equipment Layout | C2 | IFA | Not Started | [9 empty] | 336 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905-F&G Device List / Index | C1 | IFR | Not Started | [9 empty] | 330 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905-F&G Device List / Index | 0 | IFU | Not Started | [9 empty] | 330 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-LST-40905-F&G Device List / Index | C2 | IFA | Not Started | [9 empty] | 330 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901-HSE Philosophy | C1 | IFR | Completed/ Submitted | Historical | 2023-04-05 | TRN-00102 |  | E-mail | 2023-04-12 | C |  | 2023-04-19 | 51 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901-HSE Philosophy | 00 | IFU | Completed/ Submitted | Current | 2023-05-12 | TRN-00216 | [6 empty] | 51 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901-HSE Philosophy | C2 | IFA | Completed/ Submitted | Historical | 2023-04-18 | TRN-00142 | [6 empty] | 51 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40901-HSE Philosophy | C3 | IFA | Completed/ Submitted | Historical | 2023-04-28 | TRN-00169 |  | E-mail | 2023-05-11 | D |  | 2023-05-18 | 51 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40902_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40902-Fire Protection Philosophy | C1 | IFR | Completed/ Submitted | Historical | 2023-04-10 | TRN-00121 |  | E-mail | 2023-04-18 | C |  | 2023-04-25 | 52 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILF-NCPF-000-HS-PHI-40902_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40902-Fire Protection Philosophy | 00 | IFU | Completed/ Submitted | Current | 2023-05-05 | TRN-00186 | [6 empty] | 52 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILF-NCPF-000-HS-PHI-40902_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-PHI-40902-Fire Protection Philosophy | C2 | IFA | Completed/ Submitted | Historical | 2023-04-25 | TRN-00159 |  | E-mail | 2023-05-04 | D |  | 2023-05-11 | 52 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915-Fire & Gas P&ID | C1 | IFR | Not Started | [9 empty] | 340 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915-Fire & Gas P&ID | 0 | IFU | Not Started | [9 empty] | 340 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-PID-40915-Fire & Gas P&ID | C2 | IFA | Not Started | [9 empty] | 340 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904-Project HSE Plan | C1 | IFR | DIC Approved | Historical | 2023-03-28 | TRN-00072 |  | E-mail | 2023-03-29 | C |  | 2023-04-05 | 50 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904-Project HSE Plan | 00 | IFU | Completed/ Submitted | Current | 2023-04-10 | TRN-00118 | [6 empty] | 50 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-PLA-40904-Project HSE Plan | C2 | IFA | Completed/ Submitted | Historical | 2023-04-04 | TRN-00096 |  | E-mail | 2023-04-07 | D |  | 2023-04-14 | 50 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914-Fire Water Hydraulic Analysis | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00271 | [6 empty] | 339 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914-Fire Water Hydraulic Analysis | 0 | IFU | Not Started | [9 empty] | 339 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40914-Fire Water Hydraulic Analysis | C2 | IFA | Not Started | [9 empty] | 339 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916-Constructability Review Report | C1 | IFR | Not Started | [9 empty] | 341 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916-Constructability Review Report | 0 | IFU | Not Started | [9 empty] | 341 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40916-Constructability Review Report | C2 | IFA | Not Started | [9 empty] | 341 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917-SIL Assessment Report (by the third party) | C1 | IFR | Not Started | [9 empty] | 342 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917-SIL Assessment Report (by the third party) | 0 | IFU | Not Started | [9 empty] | 342 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-REP-40917-SIL Assessment Report (by the third party) | C2 | IFA | Not Started | [9 empty] | 342 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909-Hazardous Area Classification Schedule | C1 | IFR | Completed/ Submitted | Current | 2023-04-25 | TRN-00156 | [6 empty] | 334 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909-Hazardous Area Classification Schedule | 0 | IFU | Not Started | [9 empty] | 334 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-SCH-40909-Hazardous Area Classification Schedule | C2 | IFA | Not Started | [9 empty] | 334 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908-Fire & Gas System Specification | C1 | IFR | Not Started | [9 empty] | 333 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908-Fire & Gas System Specification | 0 | IFU | Not Started | [9 empty] | 333 |  |  | Folder | sites/15195/14_DELV
HS | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-HS-SPE-40908-Fire & Gas System Specification | C2 | IFA | Not Started | [9 empty] | 333 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512-Datasheet for Material Handling Equipment (EOT crane or similar) | C1 | IFR | Not Started | [9 empty] | 289 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512-Datasheet for Material Handling Equipment (EOT crane or similar) | 0 | IFU | Not Started | [9 empty] | 289 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40512-Datasheet for Material Handling Equipment (EOT crane or similar) | C2 | IFA | Not Started | [9 empty] | 289 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719-Special Item Datasheets | C1 | IFR | Not Started | [9 empty] | 276 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719-Special Item Datasheets | 0 | IFU | Not Started | [9 empty] | 276 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40719-Special Item Datasheets | C2 | IFA | Not Started | [9 empty] | 276 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762-Data Sheet for Valves | C1 | IFR | Not Started | [9 empty] | 277 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762-Data Sheet for Valves | 0 | IFU | Not Started | [9 empty] | 277 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40762-Data Sheet for Valves | C2 | IFA | Not Started | [9 empty] | 277 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763-Data Sheet for Strainers | C1 | IFR | Not Started | [9 empty] | 278 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763-Data Sheet for Strainers | 0 | IFU | Not Started | [9 empty] | 278 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40763-Data Sheet for Strainers | C2 | IFA | Not Started | [9 empty] | 278 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764-Data Sheet for Spring Supports | C1 | IFR | Not Started | [9 empty] | 279 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764-Data Sheet for Spring Supports | 0 | IFU | Not Started | [9 empty] | 279 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40764-Data Sheet for Spring Supports | C2 | IFA | Not Started | [9 empty] | 279 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765-Data Sheet for Corossion Inhibitor Access Fittings with Injection Quill | C1 | IFR | Not Started | [9 empty] | 280 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765-Data Sheet for Corossion Inhibitor Access Fittings with Injection Quill | 0 | IFU | Not Started | [9 empty] | 280 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40765-Data Sheet for Corossion Inhibitor Access Fittings with Injection Quill | C2 | IFA | Not Started | [9 empty] | 280 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722-Material Selection Diagram | C1 | IFR | Completed/ Submitted | Current | 2023-05-12 | TRN-00228 |  | E-mail | 2023-05-22 | C |  | 2023-05-29 | 283 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722-Material Selection Diagram | 0 | IFU | Not Started | [9 empty] | 283 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40722-Material Selection Diagram | C2 | IFA | Not Started | [9 empty] | 283 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723-Pipe Support Schedule | C1 | IFR | Not Started | [9 empty] | 284 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723-Pipe Support Schedule | 0 | IFU | Not Started | [9 empty] | 284 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40723-Pipe Support Schedule | C2 | IFA | Not Started | [9 empty] | 284 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724-Material Selection Diagram–Inlet Facilities | C1 | IFR | Not Started | [9 empty] | 380 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724-Material Selection Diagram–Inlet Facilities | 0 | IFU | Not Started | [9 empty] | 380 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40724-Material Selection Diagram–Inlet Facilities | C2 | IFA | Not Started | [9 empty] | 380 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725-Material Selection Diagram–Gas Conditioning Unit, Gas Export | C1 | IFR | Not Started | [9 empty] | 379 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725-Material Selection Diagram–Gas Conditioning Unit, Gas Export | 0 | IFU | Not Started | [9 empty] | 379 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40725-Material Selection Diagram–Gas Conditioning Unit, Gas Export | C2 | IFA | Not Started | [9 empty] | 379 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726-Material Selection Diagram-Condensate Stabilization | C1 | IFR | Not Started | [9 empty] | 378 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726-Material Selection Diagram-Condensate Stabilization | 0 | IFU | Not Started | [9 empty] | 378 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DIA-40726-Material Selection Diagram-Condensate Stabilization | C2 | IFA | Not Started | [9 empty] | 378 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724-Piping General Arrangement - Area 002 | C1 | IFR | Not Started | [9 empty] | 230 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724-Piping General Arrangement - Area 002 | 0 | IFU | Not Started | [9 empty] | 230 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40724-Piping General Arrangement - Area 002 | C2 | IFA | Not Started | [9 empty] | 230 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725-Piping General Arrangement - Area 003 | C1 | IFR | Not Started | [9 empty] | 231 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725-Piping General Arrangement - Area 003 | 0 | IFU | Not Started | [9 empty] | 231 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40725-Piping General Arrangement - Area 003 | C2 | IFA | Not Started | [9 empty] | 231 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726-Piping General Arrangement - Area 004 | C1 | IFR | Not Started | [9 empty] | 232 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726-Piping General Arrangement - Area 004 | 0 | IFU | Not Started | [9 empty] | 232 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40726-Piping General Arrangement - Area 004 | C2 | IFA | Not Started | [9 empty] | 232 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727-Piping General Arrangement - Area 005 | C1 | IFR | Not Started | [9 empty] | 233 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727-Piping General Arrangement - Area 005 | 0 | IFU | Not Started | [9 empty] | 233 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40727-Piping General Arrangement - Area 005 | C2 | IFA | Not Started | [9 empty] | 233 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728-Piping General Arrangement - Area 006 | C1 | IFR | Not Started | [9 empty] | 234 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728-Piping General Arrangement - Area 006 | 0 | IFU | Not Started | [9 empty] | 234 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40728-Piping General Arrangement - Area 006 | C2 | IFA | Not Started | [9 empty] | 234 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729-Piping General Arrangement - Area 007 | C1 | IFR | Not Started | [9 empty] | 235 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729-Piping General Arrangement - Area 007 | 0 | IFU | Not Started | [9 empty] | 235 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40729-Piping General Arrangement - Area 007 | C2 | IFA | Not Started | [9 empty] | 235 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730-Piping General Arrangement - Area 008 | C1 | IFR | Not Started | [9 empty] | 236 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730-Piping General Arrangement - Area 008 | 0 | IFU | Not Started | [9 empty] | 236 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40730-Piping General Arrangement - Area 008 | C2 | IFA | Not Started | [9 empty] | 236 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731-Piping General Arrangement - Area 009 | C1 | IFR | Not Started | [9 empty] | 237 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731-Piping General Arrangement - Area 009 | 0 | IFU | Not Started | [9 empty] | 237 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40731-Piping General Arrangement - Area 009 | C2 | IFA | Not Started | [9 empty] | 237 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732-Piping General Arrangement - Area 010 | C1 | IFR | Not Started | [9 empty] | 238 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732-Piping General Arrangement - Area 010 | 0 | IFU | Not Started | [9 empty] | 238 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40732-Piping General Arrangement - Area 010 | C2 | IFA | Not Started | [9 empty] | 238 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733-Piping General Arrangement - Area 011 | C1 | IFR | Not Started | [9 empty] | 239 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733-Piping General Arrangement - Area 011 | 0 | IFU | Not Started | [9 empty] | 239 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40733-Piping General Arrangement - Area 011 | C2 | IFA | Not Started | [9 empty] | 239 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734-Piping General Arrangement - Area 012 | C1 | IFR | Not Started | [9 empty] | 240 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734-Piping General Arrangement - Area 012 | 0 | IFU | Not Started | [9 empty] | 240 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40734-Piping General Arrangement - Area 012 | C2 | IFA | Not Started | [9 empty] | 240 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735-Piping General Arrangement - Area 013 | C1 | IFR | Not Started | [9 empty] | 241 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735-Piping General Arrangement - Area 013 | 0 | IFU | Not Started | [9 empty] | 241 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40735-Piping General Arrangement - Area 013 | C2 | IFA | Not Started | [9 empty] | 241 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736-Piping General Arrangement - Area 014 | C1 | IFR | Not Started | [9 empty] | 242 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736-Piping General Arrangement - Area 014 | 0 | IFU | Not Started | [9 empty] | 242 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40736-Piping General Arrangement - Area 014 | C2 | IFA | Not Started | [9 empty] | 242 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737-Piping General Arrangement - Area 015 | C1 | IFR | Not Started | [9 empty] | 243 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737-Piping General Arrangement - Area 015 | 0 | IFU | Not Started | [9 empty] | 243 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40737-Piping General Arrangement - Area 015 | C2 | IFA | Not Started | [9 empty] | 243 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738-Piping General Arrangement - Area 016 | C1 | IFR | Not Started | [9 empty] | 244 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738-Piping General Arrangement - Area 016 | 0 | IFU | Not Started | [9 empty] | 244 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40738-Piping General Arrangement - Area 016 | C2 | IFA | Not Started | [9 empty] | 244 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739-Piping General Arrangement - Area 017 | C1 | IFR | Not Started | [9 empty] | 245 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739-Piping General Arrangement - Area 017 | 0 | IFU | Not Started | [9 empty] | 245 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40739-Piping General Arrangement - Area 017 | C2 | IFA | Not Started | [9 empty] | 245 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740-Piping General Arrangement - Area 018 | C1 | IFR | Not Started | [9 empty] | 246 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740-Piping General Arrangement - Area 018 | 0 | IFU | Not Started | [9 empty] | 246 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40740-Piping General Arrangement - Area 018 | C2 | IFA | Not Started | [9 empty] | 246 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741-Piping General Arrangement - Area 019 | C1 | IFR | Not Started | [9 empty] | 247 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741-Piping General Arrangement - Area 019 | 0 | IFU | Not Started | [9 empty] | 247 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40741-Piping General Arrangement - Area 019 | C2 | IFA | Not Started | [9 empty] | 247 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742-Piping General Arrangement - Area 020 | C1 | IFR | Not Started | [9 empty] | 248 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742-Piping General Arrangement - Area 020 | 0 | IFU | Not Started | [9 empty] | 248 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40742-Piping General Arrangement - Area 020 | C2 | IFA | Not Started | [9 empty] | 248 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743-Piping General Arrangement - Area 021 | C1 | IFR | Not Started | [9 empty] | 249 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743-Piping General Arrangement - Area 021 | 0 | IFU | Not Started | [9 empty] | 249 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40743-Piping General Arrangement - Area 021 | C2 | IFA | Not Started | [9 empty] | 249 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744-Piping General Arrangement - Area 022 | C1 | IFR | Not Started | [9 empty] | 250 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744-Piping General Arrangement - Area 022 | 0 | IFU | Not Started | [9 empty] | 250 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40744-Piping General Arrangement - Area 022 | C2 | IFA | Not Started | [9 empty] | 250 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745-Piping General Arrangement - Area 023 | C1 | IFR | Not Started | [9 empty] | 251 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745-Piping General Arrangement - Area 023 | 0 | IFU | Not Started | [9 empty] | 251 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40745-Piping General Arrangement - Area 023 | C2 | IFA | Not Started | [9 empty] | 251 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746-Piping General Arrangement - Area 024 | C1 | IFR | Not Started | [9 empty] | 252 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746-Piping General Arrangement - Area 024 | 0 | IFU | Not Started | [9 empty] | 252 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40746-Piping General Arrangement - Area 024 | C2 | IFA | Not Started | [9 empty] | 252 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747-Piping General Arrangement - Area 025 | C1 | IFR | Not Started | [9 empty] | 253 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747-Piping General Arrangement - Area 025 | 0 | IFU | Not Started | [9 empty] | 253 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40747-Piping General Arrangement - Area 025 | C2 | IFA | Not Started | [9 empty] | 253 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748-Piping General Arrangement - Area 026 | C1 | IFR | Not Started | [9 empty] | 254 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748-Piping General Arrangement - Area 026 | 0 | IFU | Not Started | [9 empty] | 254 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40748-Piping General Arrangement - Area 026 | C2 | IFA | Not Started | [9 empty] | 254 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749-Piping General Arrangement - Area 027 | C1 | IFR | Not Started | [9 empty] | 255 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749-Piping General Arrangement - Area 027 | 0 | IFU | Not Started | [9 empty] | 255 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40749-Piping General Arrangement - Area 027 | C2 | IFA | Not Started | [9 empty] | 255 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750-Piping General Arrangement - Area 028 | C1 | IFR | Not Started | [9 empty] | 256 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750-Piping General Arrangement - Area 028 | 0 | IFU | Not Started | [9 empty] | 256 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40750-Piping General Arrangement - Area 028 | C2 | IFA | Not Started | [9 empty] | 256 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751-Piping General Arrangement - Unedrground Area 001 | C1 | IFR | Not Started | [9 empty] | 257 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751-Piping General Arrangement - Unedrground Area 001 | 0 | IFU | Not Started | [9 empty] | 257 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40751-Piping General Arrangement - Unedrground Area 001 | C2 | IFA | Not Started | [9 empty] | 257 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752-Piping General Arrangement - Unedrground Area 002 | C1 | IFR | Not Started | [9 empty] | 258 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752-Piping General Arrangement - Unedrground Area 002 | 0 | IFU | Not Started | [9 empty] | 258 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40752-Piping General Arrangement - Unedrground Area 002 | C2 | IFA | Not Started | [9 empty] | 258 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753-Piping General Arrangement - Unedrground Area 003 | C1 | IFR | Not Started | [9 empty] | 259 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753-Piping General Arrangement - Unedrground Area 003 | 0 | IFU | Not Started | [9 empty] | 259 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40753-Piping General Arrangement - Unedrground Area 003 | C2 | IFA | Not Started | [9 empty] | 259 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754-Piping General Arrangement - Unedrground Area 004 | C1 | IFR | Not Started | [9 empty] | 260 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754-Piping General Arrangement - Unedrground Area 004 | 0 | IFU | Not Started | [9 empty] | 260 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40754-Piping General Arrangement - Unedrground Area 004 | C2 | IFA | Not Started | [9 empty] | 260 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755-Piping General Arrangement - Unedrground Area 005 | C1 | IFR | Not Started | [9 empty] | 261 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755-Piping General Arrangement - Unedrground Area 005 | 0 | IFU | Not Started | [9 empty] | 261 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40755-Piping General Arrangement - Unedrground Area 005 | C2 | IFA | Not Started | [9 empty] | 261 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756-Piping General Arrangement - Unedrground Area 006 | C1 | IFR | Not Started | [9 empty] | 262 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756-Piping General Arrangement - Unedrground Area 006 | 0 | IFU | Not Started | [9 empty] | 262 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-DRW-40756-Piping General Arrangement - Unedrground Area 006 | C2 | IFA | Not Started | [9 empty] | 262 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707-AVEVA E3D Project Setup Guide | C1 | IFR | Completed/ Submitted | Historical | 2023-04-04 | TRN-00101 |  | E-mail | 2023-04-14 | D |  | 2023-04-21 | 88 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707-AVEVA E3D Project Setup Guide | C2 | IFA | Not Started | [9 empty] | 88 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40707-AVEVA E3D Project Setup Guide | 00 | IFU | Completed/ Submitted | Current | 2023-04-14 | TRN-00135 | [6 empty] | 88 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708-AVEVA E3D Tag Numbering System | C1 | IFR | IDCCheck completed | Historical | 2023-04-07 | TRN-00114 |  | E-mail | 2023-04-17 | D |  | 2023-04-24 | 228 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708-AVEVA E3D Tag Numbering System | 00 | IFU | Completed/ Submitted | Current | 2023-04-24 | TRN-00155 | [6 empty] | 228 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40708-AVEVA E3D Tag Numbering System | C2 | IFA | Not Started | [9 empty] | 228 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715-Pulsation Study (by third party) | C1 | IFR | Not Started | [9 empty] | 272 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715-Pulsation Study (by third party) | 0 | IFU | Not Started | [9 empty] | 272 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-GEN-40715-Pulsation Study (by third party) | C2 | IFA | Not Started | [9 empty] | 272 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711-Piping Isometrics | C1 | IFR | Not Started | [9 empty] | 263 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711-Piping Isometrics | 0 | IFU | Not Started | [9 empty] | 263 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-ISO-40711-Piping Isometrics | C2 | IFA | Not Started | [9 empty] | 263 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712-Stress Critical Line lists | C1 | IFR | Not Started | [9 empty] | 264 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712-Stress Critical Line lists | 0 | IFU | Not Started | [9 empty] | 264 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40712-Stress Critical Line lists | C2 | IFA | Not Started | [9 empty] | 264 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718-Valve List | C1 | IFR | Not Started | [9 empty] | 275 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718-Valve List | 0 | IFU | Not Started | [9 empty] | 275 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-LST-40718-Valve List | C2 | IFA | Not Started | [9 empty] | 275 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720-Piping Items MTO | C1 | IFR | Not Started | [9 empty] | 281 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720-Piping Items MTO | 0 | IFU | Not Started | [9 empty] | 281 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-MTO-40720-Piping Items MTO | C2 | IFA | Not Started | [9 empty] | 281 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703-Plot Plan - Equipment Layouts | C1 | IFR | Completed/ Submitted |  | 2023-05-19 | TRN-00247 |  | E-mail | 2023-05-26 | C |  | 2023-06-02 | 223 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703-Plot Plan - Equipment Layouts | 0 | IFU | Not Started | [9 empty] | 223 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40703-Plot Plan - Equipment Layouts | C2 | IFA | Not Started | [9 empty] | 223 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709-Key Plan | C1 | IFR | Not Started | [9 empty] | 229 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709-Key Plan | 0 | IFU | Not Started | [9 empty] | 229 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-PLA-40709-Key Plan | C2 | IFA | Not Started | [9 empty] | 229 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704-30% Model Close-out Report | C1 | IFR | Not Started | [9 empty] | 224 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704-30% Model Close-out Report | 0 | IFU | Not Started | [9 empty] | 224 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40704-30% Model Close-out Report | C2 | IFA | Not Started | [9 empty] | 224 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705-60% Model Close-out Report | C1 | IFR | Not Started | [9 empty] | 225 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705-60% Model Close-out Report | 0 | IFU | Not Started | [9 empty] | 225 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40705-60% Model Close-out Report | C2 | IFA | Not Started | [9 empty] | 225 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706-90% Model Close-out Report | C1 | IFR | Not Started | [9 empty] | 226 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706-90% Model Close-out Report | 0 | IFU | Not Started | [9 empty] | 226 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40706-90% Model Close-out Report | C2 | IFA | Not Started | [9 empty] | 226 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713-Stress Analysis Reports | C1 | IFR | Not Started | [9 empty] | 265 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713-Stress Analysis Reports | 0 | IFU | Not Started | [9 empty] | 265 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40713-Stress Analysis Reports | C2 | IFA | Not Started | [9 empty] | 265 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714-Stress Analysis Reports (Dynamic/Vibration) | C1 | IFR | Not Started | [9 empty] | 271 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714-Stress Analysis Reports (Dynamic/Vibration) | 0 | IFU | Not Started | [9 empty] | 271 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40714-Stress Analysis Reports (Dynamic/Vibration) | C2 | IFA | Not Started | [9 empty] | 271 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40721_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40721-Material Selection Report | C2 | IFA | Completed/ Submitted | Current | 2023-05-19 | TRN-00254 | [6 empty] | 282 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40721_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40721-Material Selection Report | 0 | IFU | Not Started | [9 empty] | 282 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40721_C1_IFR | 1 | NAWCPF-ILFAE-PF01-000-ME-REP-40721-Material Selection Report | C1 | IFR | Completed/ Submitted | Historical | 2023-05-05 | TRN-00195 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 282 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757-Stress Analysis Reports - System 2 | C1 | IFR | Not Started | [9 empty] | 266 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757-Stress Analysis Reports - System 2 | 0 | IFU | Not Started | [9 empty] | 266 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40757-Stress Analysis Reports - System 2 | C2 | IFA | Not Started | [9 empty] | 266 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758-Stress Analysis Reports - System 3 | C1 | IFR | Not Started | [9 empty] | 267 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758-Stress Analysis Reports - System 3 | 0 | IFU | Not Started | [9 empty] | 267 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40758-Stress Analysis Reports - System 3 | C2 | IFA | Not Started | [9 empty] | 267 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759-Stress Analysis Reports - System 4 | C1 | IFR | Not Started | [9 empty] | 268 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759-Stress Analysis Reports - System 4 | 0 | IFU | Not Started | [9 empty] | 268 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40759-Stress Analysis Reports - System 4 | C2 | IFA | Not Started | [9 empty] | 268 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760-Stress Analysis Reports - System 5 | C1 | IFR | Not Started | [9 empty] | 269 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760-Stress Analysis Reports - System 5 | 0 | IFU | Not Started | [9 empty] | 269 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40760-Stress Analysis Reports - System 5 | C2 | IFA | Not Started | [9 empty] | 269 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761-Stress Analysis Reports - System 6 | C1 | IFR | Not Started | [9 empty] | 270 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761-Stress Analysis Reports - System 6 | 0 | IFU | Not Started | [9 empty] | 270 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-REP-40761-Stress Analysis Reports - System 6 | C2 | IFA | Not Started | [9 empty] | 270 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717-Tie in Schedule | C1 | IFR | Not Started | [9 empty] | 274 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717-Tie in Schedule | 0 | IFU | Not Started | [9 empty] | 274 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-SCH-40717-Tie in Schedule | C2 | IFA | Not Started | [9 empty] | 274 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511-Specification of Material Handling Equipment | C1 | IFR | Not Started | [9 empty] | 288 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511-Specification of Material Handling Equipment | 0 | IFU | Not Started | [9 empty] | 288 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40511-Specification of Material Handling Equipment | C2 | IFA | Not Started | [9 empty] | 288 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701-Piping Material Specifications | C1 | IFR | Not Started | [9 empty] | 221 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701-Piping Material Specifications | 0 | IFU | Not Started | [9 empty] | 221 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40701-Piping Material Specifications | C2 | IFA | Not Started | [9 empty] | 221 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702-Painting Specifications | C1 | IFR | Completed/ Submitted | Historical | 2023-05-12 | TRN-00224 |  | E-mail | 2023-05-22 | D |  | 2023-05-29 | 222 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702-Painting Specifications | 00 | IFU | Completed/ Submitted | Current | 2023-05-25 | TRN-00265 | [6 empty] | 222 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40702-Painting Specifications | C2 | IFA | Not Started | [9 empty] | 222 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716-Special Piping Support Drawings | C1 | IFR | Not Started | [9 empty] | 273 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716-Special Piping Support Drawings | 0 | IFU | Not Started | [9 empty] | 273 |  |  | Folder | sites/15195/14_DELV
PP | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40716-Special Piping Support Drawings | C2 | IFA | Not Started | [9 empty] | 273 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100-Planning Package | C1 | IFR | Completed/ Submitted | Historical | 2023-02-03 | TRN-00006 |  | E-mail | 2023-02-21 | C |  | 2023-02-28 | 45 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40101_C4_IFA | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100-Planning Package | C4 | IFA | Completed/ Submitted | Historical | 2023-03-28 | TRN-00081 |  | E-mail | 2023-03-31 | D |  | 2023-04-07 | 45 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100-Planning Package | C2 | IFA | Completed/ Submitted | Historical | 2023-03-03 | TRN-00033 |  | E-mail | 2023-03-10 | C |  | 2023-03-17 | 45 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100-Planning Package | C3 | IFA | Completed/ Submitted | Current | 2023-03-17 | TRN-00057 |  | E-mail | 2023-03-27 | C |  | 2023-04-03 | 45 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PL-PLA-40100-Planning Package | 0 | IFU | Completed/ Submitted | Current | 2023-04-12 | TRN-0127 | [6 empty] | 45 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104-Basis of design | C1 | IFR | Completed/ Submitted | Historical | 2023-05-05 | TRN-00196 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 47 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104-Basis of design | 00 | IFU | Not Started | [9 empty] | 47 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104-Basis of design | C2 | IFA | Completed/ Submitted | Current | 2023-05-18 | TRN-00241 |  | E-mail | 2023-05-25 | C |  | 2023-06-01 | 47 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-BOD-40104-Basis of design | C3 | IFA | Not Started | [9 empty] | 47 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILF-NCPF-000-PM-PEP-40102_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-PEP-40102-Project Execution Plan | C1 | IFR | Completed/ Submitted | Historical | 2023-03-09 | TRN-00039 |  | E-mail | 2023-03-23 | C |  | 2023-03-30 | 44 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PEP-40102_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-PEP-40102-Project Execution Plan | 00 | IFU | Completed/ Submitted | Current | 2023-04-18 | TRN-00147 | [6 empty] | 44 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PEP-40102_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-PEP-40102-Project Execution Plan | C2 | IFA | Completed/ Submitted | Historical | 2023-04-07 | TRN-00116 |  | E-mail | 2023-04-14 | D |  | 2023-04-21 | 44 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107_C1_IFR | 5 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107-Quality Plan | C1 | IFR | IDCCheck completed | Historical | 2023-03-27 | TRN-00074 |  | E-mail | 2023-04-09 | C |  | 2023-04-16 | 10 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107_00_IFU | 3 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107-Quality Plan | 00 | IFU | Completed/ Submitted | Current | 2023-04-19 | TRN-00152 | [6 empty] | 10 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-PLA-40107-Quality Plan | C2 | IFA | Completed/ Submitted | Historical | 2023-04-12 | TRN-0126 |  | E-mail | 2023-04-18 | D |  | 2023-04-25 | 10 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-NCPF-000-PM-PRO-40106_C001_IFR | 2 | NAWCPF-ILFAE-PF01-000-PM-PRO-40106-Design Control Procedures, Design Review , Verification & Validation Procedures | C001 | IFR | IDCCheck completed | Historical | 2023-03-03 | TRN-00028 |  |  | 2023-03-10 | C |  | 2023-03-17 | 9 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PRO-40106_000_IFU | 3 | NAWCPF-ILFAE-PF01-000-PM-PRO-40106-Design Control Procedures, Design Review , Verification & Validation Procedures | 00 | IFU | Completed/ Submitted | Current | 2023-03-30 | TRN-00091 | [6 empty] | 9 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-PRO-40106_C2_IFA | 6 | NAWCPF-ILFAE-PF01-000-PM-PRO-40106-Design Control Procedures, Design Review , Verification & Validation Procedures | C2 | IFA | Completed/ Submitted | Historical | 2023-03-22 | TRN-00069 |  | E-mail | 2023-03-28 | D |  | 2023-04-04 | 9 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109-Risk Assessment Report | C1 | IFR | Completed/ Submitted | Historical | 2023-03-09 | TRN-00040 |  | E-mail | 2023-03-23 | D |  | 2023-03-30 | 64 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109-Risk Assessment Report | 00 | IFU | Completed/ Submitted | Current | 2023-03-29 | TRN-00083 | [6 empty] | 64 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40109-Risk Assessment Report | C2 | IFA | Not Started | [9 empty] | 64 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111-Operating Manuels & Procedures | C1 | IFR | Not Started | [9 empty] | 89 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111-Operating Manuels & Procedures | 0 | IFU | Not Started | [9 empty] | 89 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40111-Operating Manuels & Procedures | C2 | IFA | Not Started | [9 empty] | 89 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112-Maintenance Procedures | C1 | IFR | Not Started | [9 empty] | 90 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112-Maintenance Procedures | 0 | IFU | Not Started | [9 empty] | 90 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40112-Maintenance Procedures | C2 | IFA | Not Started | [9 empty] | 90 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-SOW-40110_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-SOW-40110-SOW of GCC | C1 | IFR | Completed/ Submitted | Historical | 2023-04-07 | TRN-00115 |  | E-mail | 2023-04-27 | B |  | 2023-05-04 | 46 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40110_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-SOW-40110-SOW of GCC | 00 | IFU | Not Started | [9 empty] | 46 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40110_C2_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-SOW-40110-SOW of GCC | C2 | IFR | Completed/ Submitted | Current | 2023-05-09 | TRN-00205 |  | E-mail | 2023-05-25 | C |  | 2023-06-01 | 46 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-REP-40110_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-SOW-40110-SOW of GCC | C3 | IFA | Not Started | [9 empty] | 46 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108-Site Visit Report | C1 | IFR | Completed/ Submitted | Historical | 2023-03-24 | TRN-00071 |  | E-mail | 2023-04-17 | C |  | 2023-04-24 | 49 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108_00_IFU | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108-Site Visit Report | 00 | IFU | Completed/ Submitted | Current | 2023-05-12 | TRN-00218 | [6 empty] | 49 |  |  | Folder | sites/15195/14_DELV
PM | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PM-SVR-40108-Site Visit Report | C2 | IFA | Completed/ Submitted | Historical | 2023-05-03 | TRN-00183 |  | E-mail | 2023-05-11 | D |  | 2023-05-18 | 49 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631-Process Design Calculations for LP Inlet Seperator | C1 | IFR | Completed/ Submitted | Current | 2023-05-10 | TRN-00211 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 352 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631-Process Design Calculations for LP Inlet Seperator | 0 | IFU | Not Started | [9 empty] | 352 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40631-Process Design Calculations for LP Inlet Seperator | C2 | IFA | Not Started | [9 empty] | 352 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632-Process Design Calculations for Fuel Gas KO Drum | C1 | IFR | Not Started | [9 empty] | 353 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632-Process Design Calculations for Fuel Gas KO Drum | 0 | IFU | Not Started | [9 empty] | 353 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40632-Process Design Calculations for Fuel Gas KO Drum | C2 | IFA | Not Started | [9 empty] | 353 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634-Process Design Calculations Test Separator NC0-V-210-0301 | C1 | IFR | Not Started | [9 empty] | 358 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634-Process Design Calculations Test Separator NC0-V-210-0301 | 0 | IFU | Not Started | [9 empty] | 358 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40634-Process Design Calculations Test Separator NC0-V-210-0301 | C2 | IFA | Not Started | [9 empty] | 358 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642-Relief Valve Sizing Memorandum | C1 | IFR | Completed/ Submitted | Current | 2023-05-12 | TRN-00222 |  | E-mail | 2023-05-18 | D |  | 2023-05-25 | 361 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642-Relief Valve Sizing Memorandum | 0 | IFU | IDC Approved | [9 empty] | 361 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-CAL-40642-Relief Valve Sizing Memorandum | C2 | IFA | Not Started | [9 empty] | 361 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637-Process Data Sheet for LP Inlet Seperator | C1 | IFR | Completed/ Submitted | Current | 2023-05-10 | TRN-00209 |  | E-mail | 2023-05-17 | C |  | 2023-05-24 | 348 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637-Process Data Sheet for LP Inlet Seperator | 0 | IFU | Not Started | [9 empty] | 348 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-DAT-40637-Process Data Sheet for LP Inlet Seperator | C2 | IFA | Not Started | [9 empty] | 348 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603-Block Flow Diagram | C1 | IFR | Completed/ Submitted | Current | 2023-05-02 | TRN-00174 |  | E-mail | 2023-05-05 | C |  | 2023-05-12 | 93 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603-Block Flow Diagram | 0 | IFU | Not Started | [9 empty] | 93 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-DBD-40603-Block Flow Diagram | C2 | IFA | Not Started | [9 empty] | 93 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644-Cause & Effect Diagram | C1 | IFR | Not Started | [9 empty] | 134 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644-Cause & Effect Diagram | 0 | IFU | Not Started | [9 empty] | 134 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-DCE-40644-Cause & Effect Diagram | C2 | IFA | Not Started | [9 empty] | 134 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647-Utility Summary | C1 | IFR | Not Started | [9 empty] | 137 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647-Utility Summary | 0 | IFU | Not Started | [9 empty] | 137 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-GEN-40647-Utility Summary | C2 | IFA | Not Started | [9 empty] | 137 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635-Equipment List | C1 | IFR | Not Started | [9 empty] | 359 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635-Equipment List | 0 | IFU | Not Started | [9 empty] | 359 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40635-Equipment List | C2 | IFA | Not Started | [9 empty] | 359 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636-Line List | C1 | IFR | Not Started | [9 empty] | 360 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636-Line List | 0 | IFU | Not Started | [9 empty] | 360 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40636-Line List | C2 | IFA | Not Started | [9 empty] | 360 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652-Alarm and Trip List | C1 | IFR | Not Started | [9 empty] | 142 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652-Alarm and Trip List | 0 | IFU | Not Started | [9 empty] | 142 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-LST-40652-Alarm and Trip List | C2 | IFA | Not Started | [9 empty] | 142 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF02-001-PR-PFD-40607_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40607-Process Flow Diagrams - Inlet Facilities | C1 | IFR | Completed/ Submitted | Current | 2023-05-15 | TRN-00233 |  | E-mail | 2023-05-19 | C |  | 2023-05-26 | 354 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-001-PR-PFD-40607_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40607-Process Flow Diagrams - Inlet Facilities | 0 | IFU | Not Started | [9 empty] | 354 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-001-PR-PFD-40607_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40607-Process Flow Diagrams - Inlet Facilities | C2 | IFA | Not Started | [9 empty] | 354 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF03-002-PR-PFD-40608_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40608-Process Flow Diagrams - Gas Conditioning Unit , Gas Export | C1 | IFR | Completed/ Submitted | Current | 2023-05-15 | TRN-00234 |  | E-mail | 2023-05-19 | C |  | 2023-05-26 | 355 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-002-PR-PFD-40608_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40608-Process Flow Diagrams - Gas Conditioning Unit , Gas Export | 0 | IFU | Not Started | [9 empty] | 355 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-002-PR-PFD-40608_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40608-Process Flow Diagrams - Gas Conditioning Unit , Gas Export | C2 | IFA | Not Started | [9 empty] | 355 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF04-003-PR-PFD-40609_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40609-Process Flow Diagrams - Condensate Stabilisation | C1 | IFR | Completed/ Submitted | Current | 2023-05-15 | TRN-00232 |  | E-mail | 2023-05-19 | C |  | 2023-05-26 | 356 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-003-PR-PFD-40609_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40609-Process Flow Diagrams - Condensate Stabilisation | 0 | IFU | Not Started | [9 empty] | 356 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-003-PR-PFD-40609_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PFD-40609-Process Flow Diagrams - Condensate Stabilisation | C2 | IFA | Not Started | [9 empty] | 356 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643-Operating, Control and Safeguarding Philosophy | C1 | IFR | Not Started | [9 empty] | 133 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643-Operating, Control and Safeguarding Philosophy | 0 | IFU | Not Started | [9 empty] | 133 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40643-Operating, Control and Safeguarding Philosophy | C2 | IFA | Not Started | [9 empty] | 133 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645-ESD and Shutdown Philosophy | C1 | IFR | Not Started | [9 empty] | 135 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645-ESD and Shutdown Philosophy | 0 | IFU | Not Started | [9 empty] | 135 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40645-ESD and Shutdown Philosophy | C2 | IFA | Not Started | [9 empty] | 135 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648-Vent and Drain Philosophy | C1 | IFR | Not Started | [9 empty] | 138 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648-Vent and Drain Philosophy | 0 | IFU | Not Started | [9 empty] | 138 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40648-Vent and Drain Philosophy | C2 | IFA | Not Started | [9 empty] | 138 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649-Isolation and Tie-in Philosophy | C1 | IFR | Completed/ Submitted | Current | 2023-05-25 | TRN-00270 | [6 empty] | 139 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649-Isolation and Tie-in Philosophy | 0 | IFU | Not Started | [9 empty] | 139 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40649-Isolation and Tie-in Philosophy | C2 | IFA | Not Started | [9 empty] | 139 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653-System Control Narrative | C1 | IFR | Not Started | [9 empty] | 143 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653-System Control Narrative | 0 | IFU | Not Started | [9 empty] | 143 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PHI-40653-System Control Narrative | C2 | IFA | Not Started | [9 empty] | 143 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609-Piping and Instrumentation Diagram - LP Inlet Separator (NC0-V-220-0201) | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00277 | [6 empty] | 99 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609-Piping and Instrumentation Diagram - LP Inlet Separator (NC0-V-220-0201) | 0 | IFU | Not Started | [9 empty] | 99 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40609-Piping and Instrumentation Diagram - LP Inlet Separator (NC0-V-220-0201) | C2 | IFA | Not Started | [9 empty] | 99 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610-Piping and Instrumentation Diagram - LP Suction Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00278 | [6 empty] | 100 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610-Piping and Instrumentation Diagram - LP Suction Header | 0 | IFU | Not Started | [9 empty] | 100 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40610-Piping and Instrumentation Diagram - LP Suction Header | C2 | IFA | Not Started | [9 empty] | 100 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611-Piping and Instrumentation Diagram - LP Discharge header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00279 | [6 empty] | 101 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611-Piping and Instrumentation Diagram - LP Discharge header | 0 | IFU | Not Started | [9 empty] | 101 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40611-Piping and Instrumentation Diagram - LP Discharge header | C2 | IFA | Not Started | [9 empty] | 101 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614-Piping and Instrumentation Diagram - Pre-Heater | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00280 | [6 empty] | 104 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614-Piping and Instrumentation Diagram - Pre-Heater | 0 | IFU | Not Started | [9 empty] | 104 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40614-Piping and Instrumentation Diagram - Pre-Heater | C2 | IFA | Not Started | [9 empty] | 104 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615-Piping and Instrumentation Diagram Legend Sheet 12 | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00281 | [6 empty] | 105 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615-Piping and Instrumentation Diagram Legend Sheet 12 | 0 | IFU | Not Started | [9 empty] | 105 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40615-Piping and Instrumentation Diagram Legend Sheet 12 | C2 | IFA | Not Started | [9 empty] | 105 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616-Piping and Instrumentation Diagram - Test separator | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00282 | [6 empty] | 106 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616-Piping and Instrumentation Diagram - Test separator | 0 | IFU | Not Started | [9 empty] | 106 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40616-Piping and Instrumentation Diagram - Test separator | C2 | IFA | Not Started | [9 empty] | 106 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers A | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00283 | [6 empty] | 107 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers A | 0 | IFU | Not Started | [9 empty] | 107 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40617-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers A | C2 | IFA | Not Started | [9 empty] | 107 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers B | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00284 | [6 empty] | 108 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers B | 0 | IFU | Not Started | [9 empty] | 108 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40618-Piping and Instrumentation Diagram - Inlet Manifold HP Production and Test Headers B | C2 | IFA | Not Started | [9 empty] | 108 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Headers A | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00285 | [6 empty] | 109 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Headers A | 0 | IFU | Not Started | [9 empty] | 109 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40619-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Headers A | C2 | IFA | Not Started | [9 empty] | 109 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Header B | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00286 | [6 empty] | 110 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Header B | 0 | IFU | Not Started | [9 empty] | 110 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40620-Piping and Instrumentation Diagram - Inlet Manifold (NC0-220-L-0401) and LP production Header B | C2 | IFA | Not Started | [9 empty] | 110 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621-Piping and Instrumentation Diagram - Inlet Separator (NC0-V-220-0403) | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00287 | [6 empty] | 111 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621-Piping and Instrumentation Diagram - Inlet Separator (NC0-V-220-0403) | 0 | IFU | Not Started | [9 empty] | 111 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40621-Piping and Instrumentation Diagram - Inlet Separator (NC0-V-220-0403) | C2 | IFA | Not Started | [9 empty] | 111 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622-Piping and Instrumentation Diagram - Export_Gas_Fiscal_Metering | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00288 | [6 empty] | 112 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622-Piping and Instrumentation Diagram - Export_Gas_Fiscal_Metering | 0 | IFU | Not Started | [9 empty] | 112 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40622-Piping and Instrumentation Diagram - Export_Gas_Fiscal_Metering | C2 | IFA | Not Started | [9 empty] | 112 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623-Piping and Instrumentation Diagram - Utility System HP/LP Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00289 | [6 empty] | 113 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623-Piping and Instrumentation Diagram - Utility System HP/LP Header | 0 | IFU | Not Started | [9 empty] | 113 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40623-Piping and Instrumentation Diagram - Utility System HP/LP Header | C2 | IFA | Not Started | [9 empty] | 113 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624-Piping and Instrumentation Diagram - Produced Water Flash Drum | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00290 | [6 empty] | 114 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624-Piping and Instrumentation Diagram - Produced Water Flash Drum | 0 | IFU | Not Started | [9 empty] | 114 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40624-Piping and Instrumentation Diagram - Produced Water Flash Drum | C2 | IFA | Not Started | [9 empty] | 114 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625-Piping and Instrumentation Diagram - Open Drain Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00291 | [6 empty] | 115 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625-Piping and Instrumentation Diagram - Open Drain Header | 0 | IFU | Not Started | [9 empty] | 115 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40625-Piping and Instrumentation Diagram - Open Drain Header | C2 | IFA | Not Started | [9 empty] | 115 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626-Piping and Instrumentation Diagram - Closed Drain Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00292 | [6 empty] | 116 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626-Piping and Instrumentation Diagram - Closed Drain Header | 0 | IFU | Not Started | [9 empty] | 116 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40626-Piping and Instrumentation Diagram - Closed Drain Header | C2 | IFA | Not Started | [9 empty] | 116 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627-Piping and Instrumentation Diagram - Plant Air Receiver | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00293 | [6 empty] | 117 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627-Piping and Instrumentation Diagram - Plant Air Receiver | 0 | IFU | Not Started | [9 empty] | 117 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40627-Piping and Instrumentation Diagram - Plant Air Receiver | C2 | IFA | Not Started | [9 empty] | 117 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628-Piping and Instrumentation Diagram - Instrument Air Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00294 | [6 empty] | 118 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628-Piping and Instrumentation Diagram - Instrument Air Header | 0 | IFU | Not Started | [9 empty] | 118 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40628-Piping and Instrumentation Diagram - Instrument Air Header | C2 | IFA | Not Started | [9 empty] | 118 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629-Piping and Instrumentation Diagram - Nitrogen Header | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00295 | [6 empty] | 119 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629-Piping and Instrumentation Diagram - Nitrogen Header | 0 | IFU | Not Started | [9 empty] | 119 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PID-40629-Piping and Instrumentation Diagram - Nitrogen Header | C2 | IFA | Not Started | [9 empty] | 119 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650-Start-up and Commissioning Philosophy/Procedure | C1 | IFR | Not Started | [9 empty] | 140 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650-Start-up and Commissioning Philosophy/Procedure | 0 | IFU | Not Started | [9 empty] | 140 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-PRO-40650-Start-up and Commissioning Philosophy/Procedure | C2 | IFA | Not Started | [9 empty] | 140 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600-CPF Design Review Verification Report | C1 | IFR | Pending DCC Check | Historical | 2023-04-17 | TRN-00138 |  | E-mail | 2023-04-18 | B |  | 2023-04-25 | 145 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600-CPF Design Review Verification Report | 0 | IFU | Not Started | [9 empty] | 145 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600-CPF Design Review Verification Report | C2 | IFA | Completed/ Submitted | Current | 2023-05-05 | TRN-00199 |  | E-mail | 2023-05-18 | C |  | 2023-05-25 | 145 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40600-CPF Design Review Verification Report | C3 | IFA | Not Started | [9 empty] | 145 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601-Process Simulation Report | C1 | IFR | Completed/ Submitted | Historical | 2023-04-13 | TRN-00129 |  | E-mail | 2023-04-18 | C |  | 2023-04-25 | 91 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601_C3_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601-Process Simulation Report | C3 | IFA | Completed/ Submitted | Current | 2023-05-16 | TRN-00236 |  | E-mail | 2023-05-24 | C |  | 2023-05-31 | 91 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601-Process Simulation Report | C2 | IFA | Completed/ Submitted | Historical | 2023-04-27 | TRN-00163 |  | E-mail | 2023-05-05 | C |  | 2023-05-12 | 91 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601-Process Simulation Report | 0 | IFU | Not Started | [9 empty] | 91 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601_C4_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40601-Process Simulation Report | C4 | IFA | Not Started | [9 empty] | 91 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602-Heat and Material Balance Report | C1 | IFR | Completed/ Submitted | Current | 2023-05-05 | TRN-00192 |  | E-mail | 2023-05-15 | C |  | 2023-05-22 | 92 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602-Heat and Material Balance Report | 0 | IFU | Not Started | [9 empty] | 92 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40602-Heat and Material Balance Report | C2 | IFA | Not Started | [9 empty] | 92 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641-Relief System Calculation Report | C1 | IFR | IDCCheck completed | Current | 2023-05-19 | TRN-00255 |  | E-mail | 2023-05-26 | E |  | 2023-06-02 | 131 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641-Relief System Calculation Report | 0 | IFU | Not Started | [9 empty] | 131 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40641-Relief System Calculation Report | C2 | IFA | Not Started | [9 empty] | 131 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646-Relief and Blowdown Study Report | C1 | IFR | Not Started | [9 empty] | 136 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646-Relief and Blowdown Study Report | 0 | IFU | Not Started | [9 empty] | 136 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40646-Relief and Blowdown Study Report | C2 | IFA | Not Started | [9 empty] | 136 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651-Hydraulic Report | C1 | IFR | Not Started | [9 empty] | 141 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651-Hydraulic Report | 0 | IFU | Not Started | [9 empty] | 141 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40651-Hydraulic Report | C2 | IFA | Not Started | [9 empty] | 141 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654_C1_IFR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654-Dispersion Simulations and Studies Report | C1 | IFR | Not Started | [9 empty] | 144 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654_0_IFU | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654-Dispersion Simulations and Studies Report | 0 | IFU | Not Started | [9 empty] | 144 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654_C2_IFA | 0 | NAWCPF-ILFAE-PF01-000-PR-REP-40654-Dispersion Simulations and Studies Report | C2 | IFA | Not Started | [9 empty] | 144 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241-Design Calculation for LP Condensate Pumps Foundation | C1 | IFR | Not Started | [9 empty] | 304 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241-Design Calculation for LP Condensate Pumps Foundation | 0 | IFU | Not Started | [9 empty] | 304 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-CV-CAL-40241-Design Calculation for LP Condensate Pumps Foundation | C2 | IFA | Not Started | [9 empty] | 304 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517-TBEs for Condensate Pump Package | C1 | IFR | Not Started | [9 empty] | 294 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517-TBEs for Condensate Pump Package | 0 | IFU | Not Started | [9 empty] | 294 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-ME-BID-40517-TBEs for Condensate Pump Package | C2 | IFA | Not Started | [9 empty] | 294 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503-Datasheet for LP Condensate Pump | C1 | IFR | Not Started | [9 empty] | 54 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503_00_IFU | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503-Datasheet for LP Condensate Pump | 00 | IFU | Not Started | [9 empty] | 54 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-ME-DAT-40503-Datasheet for LP Condensate Pump | C2 | IFA | Not Started | [9 empty] | 54 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727-Material Selection Diagram-LP Separator and Condensate Pumps | C1 | IFR | Not Started | [9 empty] | 377 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727-Material Selection Diagram-LP Separator and Condensate Pumps | 0 | IFU | Not Started | [9 empty] | 377 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-ME-DIA-40727-Material Selection Diagram-LP Separator and Condensate Pumps | C2 | IFA | Not Started | [9 empty] | 377 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516-MRs for Condensate Pump Package | C1 | IFR | Not Started | [9 empty] | 293 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516-MRs for Condensate Pump Package | 0 | IFU | Not Started | [9 empty] | 293 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-ME-GEN-40516-MRs for Condensate Pump Package | C2 | IFA | Not Started | [9 empty] | 293 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508-Specification for Condensate Pump Package | C1 | IFR | Not Started | [9 empty] | 287 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508-Specification for Condensate Pump Package | 0 | IFU | Not Started | [9 empty] | 287 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-ME-SPE-40508-Specification for Condensate Pump Package | C2 | IFA | Not Started | [9 empty] | 287 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633-Process Design Calculations for Condensate Pumps | C1 | IFR | Not Started | [9 empty] | 357 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633-Process Design Calculations for Condensate Pumps | 0 | IFU | Not Started | [9 empty] | 357 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-PR-CAL-40633-Process Design Calculations for Condensate Pumps | C2 | IFA | Not Started | [9 empty] | 357 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639-Process Data Sheet for LP Condensate Pump | C1 | IFR | Not Started | [9 empty] | 350 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639-Process Data Sheet for LP Condensate Pump | 0 | IFU | Not Started | [9 empty] | 350 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-PR-DAT-40639-Process Data Sheet for LP Condensate Pump | C2 | IFA | Not Started | [9 empty] | 350 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606-Process Flow Diagrams - LP Separator and Condensate Pumps | C1 | IFR | Completed/ Submitted | Current | 2023-05-08 | TRN-00202 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 96 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606-Process Flow Diagrams - LP Separator and Condensate Pumps | 0 | IFU | Not Started | [9 empty] | 96 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-PR-PFD-40606-Process Flow Diagrams - LP Separator and Condensate Pumps | C2 | IFA | Not Started | [9 empty] | 96 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613_C1_IFR | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613-Piping and Instrumentation Diagram - Condensate Pump Module | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00296 | [6 empty] | 103 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613_0_IFU | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613-Piping and Instrumentation Diagram - Condensate Pump Module | 0 | IFU | Not Started | [9 empty] | 103 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613_C2_IFA | 0 | NAWCPF-ILFAE-PF01-200-PR-PID-40613-Piping and Instrumentation Diagram - Condensate Pump Module | C2 | IFA | Not Started | [9 empty] | 103 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242-Design Calculation for Inlet Manifolds Foundation | C1 | IFR | Not Started | [9 empty] | 305 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242-Design Calculation for Inlet Manifolds Foundation | 0 | IFU | Not Started | [9 empty] | 305 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40242-Design Calculation for Inlet Manifolds Foundation | C2 | IFA | Not Started | [9 empty] | 305 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243-Design Calculation for LP Inlet Separator Foundation | C1 | IFR | Not Started | [9 empty] | 306 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243-Design Calculation for LP Inlet Separator Foundation | 0 | IFU | Not Started | [9 empty] | 306 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-CV-CAL-40243-Design Calculation for LP Inlet Separator Foundation | C2 | IFA | Not Started | [9 empty] | 306 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229-Foundation Plan & Details of Inlet Manifolds | C1 | IFR | Not Started | [9 empty] | 296 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229-Foundation Plan & Details of Inlet Manifolds | 0 | IFU | Not Started | [9 empty] | 296 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40229-Foundation Plan & Details of Inlet Manifolds | C2 | IFA | Not Started | [9 empty] | 296 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230-Foundation Plan & Details of LP Inlet Separator | C1 | IFR | Not Started | [9 empty] | 371 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230-Foundation Plan & Details of LP Inlet Separator | 0 | IFU | Not Started | [9 empty] | 371 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-CV-DRW-40230-Foundation Plan & Details of LP Inlet Separator | C2 | IFA | Not Started | [9 empty] | 371 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514-TBEs for LP Inlet Separator Package | C1 | IFR | Not Started | [9 empty] | 291 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514-TBEs for LP Inlet Separator Package | 0 | IFU | Not Started | [9 empty] | 291 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-ME-BID-40514-TBEs for LP Inlet Separator Package | C2 | IFA | Not Started | [9 empty] | 291 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501-Datasheet for LP Inlet Separator | C1 | IFR | Completed/ Submitted | Historical | 2023-05-12 | TRN-00221 |  | E-mail | 2023-05-19 | C |  | 2023-05-26 | 53 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501_00_IFU | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501-Datasheet for LP Inlet Separator | 00 | IFU | Not Started | [9 empty] | 53 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-ME-DAT-40501-Datasheet for LP Inlet Separator | C2 | IFA | Completed/ Submitted | Current | 2023-05-23 | TRN-00260 | [6 empty] | 53 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513-MRs for LP Inlet Separator Package | C1 | IFR | Completed/ Submitted | Historical | 2023-04-26 | TRN-00159 |  | E-mail | 2023-05-04 | C |  | 2023-05-11 | 290 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513_0_IFU | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513-MRs for LP Inlet Separator Package | 0 | IFU | Not Started | [9 empty] | 290 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-ME-GEN-40513-MRs for LP Inlet Separator Package | C2 | IFA | Completed/ Submitted | Current | 2023-05-11 | TRN-00214 |  | E-mail | 2023-05-19 | D |  | 2023-05-26 | 290 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506_C1_IFR | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506-Specification for LP Inlet Separator Package | C1 | IFR | Completed/ Submitted | Historical | 2023-04-04 | TRN-00099 |  | E-mail | 2023-04-12 | C |  | 2023-04-19 | 285 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506_00_IFU | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506-Specification for LP Inlet Separator Package | 00 | IFU | Completed/ Submitted | Current | 2023-05-12 | TRN-00225 | [6 empty] | 285 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506_C2_IFA | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506-Specification for LP Inlet Separator Package | C2 | IFA | Completed/ Submitted | Historical | 2023-04-18 | TRN-00141 |  | E-mail | 2023-04-27 | C |  | 2023-05-04 | 285 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506_C3_IFA | 0 | NAWCPF-ILFAE-PF01-220-ME-SPE-40506-Specification for LP Inlet Separator Package | C3 | IFA | Completed/ Submitted | Historical | 2023-05-03 | TRN-00181 |  | E-mail | 2023-05-11 | D |  | 2023-05-18 | 285 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422-IO List Front end Compression | C1 | IFR | Not Started | [9 empty] | 161 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422-IO List Front end Compression | 0 | IFU | Not Started | [9 empty] | 161 |  |  | Folder | sites/15195/14_DELV
IC | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CI-LST-40422-IO List Front end Compression | C2 | IFA | Not Started | [9 empty] | 161 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235-Design Calculation for LP Compressor Foundation | C1 | IFR | Not Started | [9 empty] | 298 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235-Design Calculation for LP Compressor Foundation | 0 | IFU | Not Started | [9 empty] | 298 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40235-Design Calculation for LP Compressor Foundation | C2 | IFA | Not Started | [9 empty] | 298 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236-Design Calculation for LP Compressor Gas Cooler Foundation | C1 | IFR | Not Started | [9 empty] | 299 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236-Design Calculation for LP Compressor Gas Cooler Foundation | 0 | IFU | Not Started | [9 empty] | 299 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40236-Design Calculation for LP Compressor Gas Cooler Foundation | C2 | IFA | Not Started | [9 empty] | 299 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237-Design Calculation for LP Compressor Shelter Foundation | C1 | IFR | Not Started | [9 empty] | 300 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237-Design Calculation for LP Compressor Shelter Foundation | 0 | IFU | Not Started | [9 empty] | 300 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40237-Design Calculation for LP Compressor Shelter Foundation | C2 | IFA | Not Started | [9 empty] | 300 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253-Design Calculation for LP Compressor Shelter | C1 | IFR | Not Started | [9 empty] | 316 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253-Design Calculation for LP Compressor Shelter | 0 | IFU | Not Started | [9 empty] | 316 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-CAL-40253-Design Calculation for LP Compressor Shelter | C2 | IFA | Not Started | [9 empty] | 316 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222-Foundations Plan & Details of LP Compressor | C1 | IFR | Not Started | [9 empty] | 32 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222_00_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222-Foundations Plan & Details of LP Compressor | 00 | IFU | Not Started | [9 empty] | 32 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40222-Foundations Plan & Details of LP Compressor | C2 | IFA | Not Started | [9 empty] | 32 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223-Foundation Plans & Details of LP Compressor Gas Cooler | C1 | IFR | Not Started | [9 empty] | 33 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223_00_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223-Foundation Plans & Details of LP Compressor Gas Cooler | 00 | IFU | Not Started | [9 empty] | 33 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40223-Foundation Plans & Details of LP Compressor Gas Cooler | C2 | IFA | Not Started | [9 empty] | 33 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224-Foundation Plan & Details of LP Compressor Shelter | C1 | IFR | Not Started | [9 empty] | 34 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224_00_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224-Foundation Plan & Details of LP Compressor Shelter | 00 | IFU | Not Started | [9 empty] | 34 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40224-Foundation Plan & Details of LP Compressor Shelter | C2 | IFA | Not Started | [9 empty] | 34 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247-Structural Steel Plan & Details of LP Compressor Shelter | C1 | IFR | Not Started | [9 empty] | 310 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247-Structural Steel Plan & Details of LP Compressor Shelter | 0 | IFU | Not Started | [9 empty] | 310 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-CV-DRW-40247-Structural Steel Plan & Details of LP Compressor Shelter | C2 | IFA | Not Started | [9 empty] | 310 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515-TBEs for LP Compressor Package | C1 | IFR | Not Started | [9 empty] | 292 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515-TBEs for LP Compressor Package | 0 | IFU | Not Started | [9 empty] | 292 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-BID-40515-TBEs for LP Compressor Package | C2 | IFA | Not Started | [9 empty] | 292 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILF-NCPF-000-ME-DAT-40502_C001_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-DAT-40502-Datasheet for LP Compressor Package | C001 | IFR | Completed/ Submitted | Historical | 2023-03-02 | TRN-00023 |  | E-mail | 2023-03-16 | C |  | 2023-03-23 | 7 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-DAT-40502_00_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-DAT-40502-Datasheet for LP Compressor Package | 00 | IFU | Completed/ Submitted | Current | 2023-04-10 | TRN-00120 | [6 empty] | 7 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILF-NCPF-000-ME-DAT-40502_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-DAT-40502-Datasheet for LP Compressor Package | C2 | IFA | Completed/ Submitted | Historical | 2023-03-24 | TRN-00073 |  | E-mail | 2023-04-05 | D |  | 2023-04-12 | 7 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728-Material Selection Diagram-LP Compressor Package A, Suction and Discharge Headers | C1 | IFR | Not Started | [9 empty] | 376 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728-Material Selection Diagram-LP Compressor Package A, Suction and Discharge Headers | 0 | IFU | Not Started | [9 empty] | 376 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40728-Material Selection Diagram-LP Compressor Package A, Suction and Discharge Headers | C2 | IFA | Not Started | [9 empty] | 376 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729-Material Selection Diagram-LP Compressor Package B | C1 | IFR | Not Started | [9 empty] | 375 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729-Material Selection Diagram-LP Compressor Package B | 0 | IFU | Not Started | [9 empty] | 375 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-DIA-40729-Material Selection Diagram-LP Compressor Package B | C2 | IFA | Not Started | [9 empty] | 375 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-000-ME-SPE-40509_C001_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509-Specification for LP Compressor Package | C001 | IFR | Completed/ Submitted | Historical | 2023-03-01 | TRN-00021 |  |  | 2023-03-08 | C |  | 2023-03-15 | 8 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509_00_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509-Specification for LP Compressor Package | 00 | IFU | Completed/ Submitted | Current | 2023-04-14 | TRN-00132 | [6 empty] | 8 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILF-NCPF-000-ME-SPE-40509_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509-Specification for LP Compressor Package | C2 | IFA | Completed/ Submitted | Historical | 2023-03-14 | TRN-00050 |  | E-mail | 2023-03-24 | C |  | 2023-03-31 | 8 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509_C3_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40509-Specification for LP Compressor Package | C3 | IFA | Completed/ Submitted | Historical | 2023-04-04 | TRN-00094 |  | E-mail | 2023-04-13 | D |  | 2023-04-20 | 8 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518-Performance Test Criteria for LP Compressors | C1 | IFR | Completed/ Submitted | Current | 2023-05-10 | TRN-00212 |  | E-mail | 2023-05-18 | C |  | 2023-05-25 | 346 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518-Performance Test Criteria for LP Compressors | 0 | IFU | Not Started | [9 empty] | 346 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-ME-SPE-40518-Performance Test Criteria for LP Compressors | C2 | IFA | Not Started | [9 empty] | 346 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638-Process Data Sheet for LP Compressor Package | C1 | IFR | Completed/ Submitted | Current | 2023-05-10 | TRN-00208 | [6 empty] | 349 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638-Process Data Sheet for LP Compressor Package | 0 | IFU | Not Started | [9 empty] | 349 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-PR-DAT-40638-Process Data Sheet for LP Compressor Package | C2 | IFA | Not Started | [9 empty] | 349 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604-Process Flow Diagrams - LP Compressors Package A | C1 | IFR | Completed/ Submitted | Current | 2023-05-08 | TRN-00201 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 94 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604-Process Flow Diagrams - LP Compressors Package A | 0 | IFU | Not Started | [9 empty] | 94 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40604-Process Flow Diagrams - LP Compressors Package A | C2 | IFA | Not Started | [9 empty] | 94 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605-Process Flow Diagrams - LP Compressors Package B | C1 | IFR | Completed/ Submitted | Current | 2023-05-08 | TRN-00200 |  | E-mail | 2023-05-16 | C |  | 2023-05-23 | 95 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605-Process Flow Diagrams - LP Compressors Package B | 0 | IFU | Not Started | [9 empty] | 95 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-PR-PFD-40605-Process Flow Diagrams - LP Compressors Package B | C2 | IFA | Not Started | [9 empty] | 95 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 A) | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00297 | [6 empty] | 97 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 A) | 0 | IFU | Not Started | [9 empty] | 97 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40607-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 A) | C2 | IFA | Not Started | [9 empty] | 97 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608_C1_IFR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 B) | C1 | IFR | Completed/ Submitted | Current | 2023-05-26 | TRN-00298 | [6 empty] | 98 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608_0_IFU | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 B) | 0 | IFU | Not Started | [9 empty] | 98 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608_C2_IFA | 0 | NAWCPF-ILFAE-PF01-231-PR-PID-40608-Piping & Instrumentation Diagram – LP Compressor Package (NC0-PK-231-0201 B) | C2 | IFA | Not Started | [9 empty] | 98 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244-Design Calculation for Fuel Gas Package Foundation | C1 | IFR | Not Started | [9 empty] | 307 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244-Design Calculation for Fuel Gas Package Foundation | 0 | IFU | Not Started | [9 empty] | 307 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-CV-CAL-40244-Design Calculation for Fuel Gas Package Foundation | C2 | IFA | Not Started | [9 empty] | 307 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231-Foundation Layout Plan of Fuel Gas Package | C1 | IFR | Not Started | [9 empty] | 372 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231-Foundation Layout Plan of Fuel Gas Package | 0 | IFU | Not Started | [9 empty] | 372 |  |  | Folder | sites/15195/14_DELV
CV | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-CV-DRW-40231-Foundation Layout Plan of Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 372 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504-Datasheet for Fuel Gas Package | C1 | IFR | Not Started | [9 empty] | 55 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504_00_IFU | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504-Datasheet for Fuel Gas Package | 00 | IFU | Not Started | [9 empty] | 55 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-ME-DAT-40504-Datasheet for Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 55 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518-Material Selection Diagram-Fuel Gas Package | C1 | IFR | Not Started | [9 empty] | 374 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518-Material Selection Diagram-Fuel Gas Package | 0 | IFU | Not Started | [9 empty] | 374 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-ME-DIA-40518-Material Selection Diagram-Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 374 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507-Specification for Fuel Gas Package | C1 | IFR | Not Started | [9 empty] | 286 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507-Specification for Fuel Gas Package | 0 | IFU | Not Started | [9 empty] | 286 |  |  | Folder | sites/15195/14_DELV
ME | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-ME-SPE-40507-Specification for Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 286 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640-Process Data Sheet for Fuel Gas Package | C1 | IFR | Completed/ Submitted | Current | 2023-05-12 | TRN-00223 |  | E-mail | 2023-05-19 | D |  | 2023-05-26 | 351 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640_00_IFU | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640-Process Data Sheet for Fuel Gas Package | 00 | IFU | Not Started | [9 empty] | 351 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-PR-DAT-40640-Process Data Sheet for Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 351 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612-Piping and Instrumentation Diagram - Fuel Gas Package | C1 | IFR | IDCCheck completed | [9 empty] | 102 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612-Piping and Instrumentation Diagram - Fuel Gas Package | 0 | IFU | Not Started | [9 empty] | 102 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40612-Piping and Instrumentation Diagram - Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 102 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40630_C1_IFR | 0 | NAWCPF-ILFAE-PF01-450-PR-UFD-40630-Utility Flow Diagram - Fuel Gas Package | C1 | IFR | Completed/ Submitted | Current | 2023-05-10 | TRN-00210 |  | E-mail | 2023-05-17 | C |  | 2023-05-24 | 120 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40630_0_IFU | 0 | NAWCPF-ILFAE-PF01-450-PR-UFD-40630-Utility Flow Diagram - Fuel Gas Package | 0 | IFU | Not Started | [9 empty] | 120 |  |  | Folder | sites/15195/14_DELV
PR | 0 | NAWCPF-ILFAE-PF01-450-PR-PID-40630_C2_IFA | 0 | NAWCPF-ILFAE-PF01-450-PR-UFD-40630-Utility Flow Diagram - Fuel Gas Package | C2 | IFA | Not Started | [9 empty] | 120 |  |  | Folder | sites/15195/14_DELV